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Brook Hollow Solar
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, CU-01 Archaeological Resources, in the Cultural Resources section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-15

	Row in the matrix
	CU-01 Archaeological Resources


1 Finding
Unknown  Evidence insufficient to rate; an information request is listed
	The rule
	Code computed the rating from the assessor's inputs:
present=unknown -> Unknown (abstain)
Set by the rule

	Decision
	Abstained (information request)

	Evidence state
	MISSING · no evidence in hand


The assessor's comments
No cultural resources desktop review, Phase I archaeological survey or SHPO/THPO correspondence is included in the data room. Archaeological resources, cemeteries and tribal cultural resources are not addressed. A state site file review would settle presence.
Conclusion withheld
	Question
	Are recorded archaeological sites, cemeteries or tribal cultural resources present in the study area?

	Missing evidence
	Cultural resources desktop review, Phase I archaeological survey, and SHPO/THPO correspondence.

	Consequence
	Presence, extent and Section 106 pathway cannot be rated; possible schedule and cost exposure remains unquantified.

	Information request
	Provide any cultural resources review, SHPO site file search results or SHPO/THPO correspondence for Brook Hollow Solar.

	Blocks the decision
	No


2 What the record shows
The five inputs
Present: unknown
No claims address recorded archaeological sites, cemeteries or tribal cultural resources. The only related claim (C-18f20d1141) concerns a farm debris pile, not cultural resources. Silence is not evidence of absence.
Cites C-18f20d1141
Extent: unknown
No cultural resources documented, so position relative to buildable area cannot be assessed.
Cites no claim.
Avoidable: unknown
Not established; no sites or high-potential areas are documented.
Cites no claim.
Pathway: none
Placeholder because presence is unknown.
Cites no claim.
Impact likely: no
Placeholder because presence is unknown.
Cites no claim.
Supporting statements (1)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-18f20d1141
A small de minimis farm debris pile was observed near the Parcel 12 barn; removal is recommended.
Quoted from page 1
A small farm debris pile (de minimis) was observed near the Parcel 12 barn; removal is recommended.
Phase I ESA 2023-01-20 · DR-0004 · Page 1 · 2023-01-20
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-01, EN-04, CU-02 · Filed under EN-01, EN-04
3 Permits and requirements
The requirements tied to the rows of this report, by level.
Engine 0.1.0, which made this run, wrote no timelines or citations of law.
Federal (1)
Section 106 consultation
F-NHPA106 · Lead federal agency with the State Historic Preservation Office (and THPOs)
	Applicability
	Conditional

	Instrument
	National Historic Preservation Act Section 106 (54 U.S.C. 306108); 36 CFR Part 800

	Trigger
	Federal nexus, for example an individual Section 404 permit or federal funding.

	Description
	A federal undertaking (federal permit, funding, license or land) must take into account effects on historic properties.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-NHPA106


State (1)
SHPO review; Section 106 consultation if a federal nexus exists; DNR Archaeology Plan/Permit for state-land or discovered human remains
S-06 · Indiana DNR Division of Historic Preservation and Archaeology (SHPO)
	Applicability
	Conditional

	Instrument
	IC 14-21-1 Historic Preservation and Archaeology Act, state permit

	Trigger
	Federal nexus (e.g. 404 permit) or discovery of burials/archaeological artifacts

	Description
	No general state review for private land without a state or federal nexus, but SHPO consultation is triggered through federal permits. Inadvertent discovery of human remains or burials requires DNR notification under IC 14-21-1.

	As of the cut-off
	As of 2023-08-15. Federal nexus is missing from the project facts.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-06


4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
High priority (1)
IR-1be216979f · High priority
Provide the shpo / thpo correspondence for the project area, or confirm none exists.
	Missing evidence
	SHPO / THPO correspondence

	Consequence
	Archaeological Resources is rated on no evidence without it.

	Blocks the decision
	Yes

	Raised by
	completeness


Medium priority (1)
IR-00324803c2 · Medium priority
Are recorded archaeological sites, cemeteries or tribal cultural resources present in the study area?
	Missing evidence
	Cultural resources desktop review, Phase I archaeological survey, and SHPO/THPO correspondence.

	Consequence
	Presence, extent and Section 106 pathway cannot be rated; possible schedule and cost exposure remains unquantified.

	Blocks the decision
	No

	Raised by
	abstention


5 Next steps and agencies
Next steps
Commission cultural resources desktop review of Indiana SHPO site files.
Phase I archaeological survey of disturbance areas if review indicates potential.
Request any existing SHPO/THPO correspondence from the developer.
Agencies
Indiana DNR DHPA (SHPO)
THPO
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-15.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (1)
Phase I ESA 2023-01-20 · DR-0004 · 2023-01-20 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-15

	Engine version
	0.1.0

	Prompt version
	2026-10-02.1

	Rows pack
	rows.json sha256 d1df27b21f79b09d

	Federal pack
	federal.json sha256 aa17c41356542d46

	State pack
	none

	Local pack
	Not written by this engine

	Data room manifest
	6141b7dc1f8441489d39e4023d551e4c0021a37ce4f9ad157607d9096c58bfb5

	Audit chain
	valid (92 events)

	QA status
	PASS

	Rendered at
	2026-10-01T21:09:12+00:00

	Run record (annex)
	a03418c2562baa8a57b7c256ce665acd2c20e92d06e365604d162e9029f8fdd6

	Exporter
	Prism/room/exporter 1.4.0
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