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Brook Hollow Solar
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, EC-02 Non-RTE Species, in the Ecological Resources section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-15

	Row in the matrix
	EC-02 Non-RTE Species


1 Finding
2  Impacts likely but may be easily resolved
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released

	Evidence state
	INFERRED · reasoned from several records


The assessor's comments
Scattered woodlots occur along Sugar Run, and field delineation identified four wetlands totaling 6.2 acres and three streams, providing migratory bird habitat. No avian or eagle nest survey or wildlife agency correspondence is in the data room.
2 What the record shows
The five inputs
Present: yes
Woodlots along Sugar Run (C-71ef7a1eed) and delineated forested/emergent wetlands and a perennial stream (C-473bc604fa, C-b2682b602a) provide suitable habitat for migratory birds and general wildlife. No bird or eagle survey is in the data room, so presence is based on habitat, not documented use.
Cites C-71ef7a1eed, C-473bc604fa, C-b2682b602a
Extent: unknown
Woodlots are described only as scattered along Sugar Run (C-71ef7a1eed); wetlands total 6.2 acres across a 1,356-acre area (C-473bc604fa). Habitat position relative to the buildable area is not documented, so extent cannot be set as core or peripheral.
Cites C-71ef7a1eed, C-473bc604fa
Avoidable: yes
Scattered woodlots and limited wetland acreage can typically be handled by clearing outside the nesting season and by siting around the Sugar Run corridor (C-71ef7a1eed, C-b2682b602a). This is a judgment; no eagle nest information is available.
Cites C-71ef7a1eed, C-b2682b602a
Pathway: standard
MBTA compliance is by avoidance (F-MBTA), through seasonal clearing restrictions. No eagle nests are documented, so an individual eagle permit is not indicated on current evidence (C-71ef7a1eed).
Cites C-71ef7a1eed
Impact likely: yes
A typical solar build involves grading, tree clearing and crossings of Sugar Run, which would likely disturb woodlot and stream-corridor habitat used by migratory birds (C-71ef7a1eed, C-b2682b602a). Impact is mainly timing.
Cites C-71ef7a1eed, C-b2682b602a
Supporting statements (3)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-473bc604fa
Field delineation on April 10-14, 2023 identified four wetlands totaling 6.2 acres (palustrine emergent and forested) and three streams within the Project Area.
Quoted from page 2
identified four wetlands totaling 6.2 acres
(palustrine emergent and palustrine forested) and three streams within the Project Area.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by AQ-01 · Filed under AQ-01
C-71ef7a1eed
Scattered woodlots occur along Sugar Run.
Quoted from page 1
scattered woodlots along Sugar Run
Brook Hollow Project Overview 2023-03-15 · DR-0001 · Page 1 · 2023-03-15
Source developer_document · Claim type presence · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by EC-01, EN-01 · Filed under AQ-01, EC-02, EN-01
C-b2682b602a
Sugar Run, a perennial stream, bisects the center of the Project Area from north to south.
Quoted from page 2
Sugar Run, a perennial stream, bisects the center of the Project Area from north to south.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by AQ-01, AQ-02 · Filed under AQ-01
3 Permits and requirements
The requirements tied to the rows of this report, by level.
Engine 0.1.0, which made this run, wrote no timelines or citations of law.
Federal (2)
Compliance through avoidance (no incidental take permit program)
F-MBTA · U.S. Fish and Wildlife Service
	Applicability
	Conditional

	Instrument
	Migratory Bird Treaty Act (16 U.S.C. 703-712); 50 CFR Parts 10 and 21

	Trigger
	Vegetation clearing or construction where migratory birds nest.

	Description
	Prohibits take of migratory birds, nests and eggs. Managed by clearing vegetation outside the nesting season and avoiding active nests.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-MBTA


Eagle nest buffers; eagle incidental take permit if disturbance cannot be avoided
F-BGEPA · U.S. Fish and Wildlife Service
	Applicability
	Conditional

	Instrument
	Bald and Golden Eagle Protection Act (16 U.S.C. 668-668d); 50 CFR Part 22

	Trigger
	Eagle nests or concentration areas near construction.

	Description
	Protects bald and golden eagles, their nests and eggs from take, including disturbance.

	As of the cut-off
	Changed after the cut-off (not applied): Revised eagle permit regulations (including general permits) took effect. (2024-04-12)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-BGEPA


State (1)
Environmental review request for state endangered and threatened species
S-05 · Indiana DNR Division of Fish & Wildlife / Nature Preserves; USFWS Bloomington field office
	Applicability
	Likely

	Instrument
	Natural Heritage Database review and state-listed species review (IC 14-31, 312 IAC 9)

	Trigger
	Always for screening; tree clearing and stream work raise risk

	Description
	Request a DNR Environmental Review for state-listed species and natural heritage. Indiana bat and northern long-eared bat tree clearing windows are commonly recommended.

	As of the cut-off
	As of 2023-08-15. NLEB was reclassified as federally endangered effective March 2023.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-05


4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
Medium priority (2)
IR-c5e9053166 · Medium priority
Provide the eagle nest review or avian survey for the project area, or confirm none exists.
	Missing evidence
	Eagle nest review or avian survey

	Consequence
	Non-RTE Species is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


IR-8469920792 · Medium priority
Provide the wildlife agency correspondence for the project area, or confirm none exists.
	Missing evidence
	Wildlife agency correspondence

	Consequence
	Non-RTE Species is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Site visit to confirm habitat and screen for eagle nests.
Site around woodlots and Sugar Run; clear trees outside nesting season.
Request USFWS/Indiana DNR review.
Agencies
USFWS
Indiana DNR
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-15.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (2)
Wetland and Stream Delineation Report May2023 · DR-0005 · 2023-05-22 · page 2
Brook Hollow Project Overview 2023-03-15 · DR-0001 · 2023-03-15 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-15

	Engine version
	0.1.0

	Prompt version
	2026-10-02.1

	Rows pack
	rows.json sha256 d1df27b21f79b09d

	Federal pack
	federal.json sha256 aa17c41356542d46

	State pack
	none

	Local pack
	Not written by this engine

	Data room manifest
	6141b7dc1f8441489d39e4023d551e4c0021a37ce4f9ad157607d9096c58bfb5

	Audit chain
	valid (92 events)

	QA status
	PASS

	Rendered at
	2026-10-01T21:09:12+00:00

	Run record (annex)
	a03418c2562baa8a57b7c256ce665acd2c20e92d06e365604d162e9029f8fdd6

	Exporter
	Prism/room/exporter 1.4.0
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