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Other: desk report
Brook Hollow Solar
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, PE-03 Other, in the Additional Permitting section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-15

	Row in the matrix
	PE-03 Other


1 Finding
2  Impacts likely but may be easily resolved
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released with flags

	The engine's reasons
	Agencies not in the register or the evidence: EPA, USACE, Transmission line owner (to be identified)

	Evidence state
	INFERRED · reasoned from several records


The assessor's comments
An existing 138 kV transmission line crosses the eastern portion of the Project Area; crossing or encroachment coordination is likely. Line ownership and terms are not documented. No federal land, funding or permit is documented in the data room. Sugar Run and tributaries are likely jurisdictional waters.
2 What the record shows
The five inputs
Present: yes
C-fe67965fc1 documents an existing 138 kV transmission line crossing the eastern Project Area, so utility crossing or encroachment coordination is a reasonable expectation for a solar build. F-SPCC is conditional on oil volume above the threshold, which is not documented; SPCC applicability is therefore a possibility, not a documented need. No federal land, funding or permit is documented. C-c601777a50 (likely jurisdictional waters) points to a possible Section 404 nexus, but whether impacts occur is undetermined. L-03 (applies) is a local approval addressed in the local zoning row.
Cites C-fe67965fc1, C-c601777a50
Extent: unknown
C-fe67965fc1 places the line in the eastern portion but does not show how much of the 1,356-acre site it affects, and no layout is documented. No project-wide federal nexus is documented, so NEPA is not shown to cover the whole project. Extent cannot be established from the evidence.
Cites C-fe67965fc1
Avoidable: yes
Line ownership and crossing terms are not documented. As a professional judgment, utility crossing agreements and SPCC plans are typically routine, and no evidence of a realistic denial exists. A federal nexus is not documented, so no discretionary approval is shown.
Cites C-fe67965fc1
Pathway: standard
Judgment: a crossing or encroachment agreement with the line owner (owner undocumented) and a possible SPCC plan follow standard processes. No federal nexus requiring an EA or EIS is documented. A Section 404 nationwide permit tied to C-c601777a50 would also be standard if wetland impacts occur.
Cites C-fe67965fc1, C-c601777a50
Impact likely: yes
Judgment, not documented layout: collection-line, access road and fence work on a site crossed by an existing 138 kV line will typically need crossing or encroachment coordination (C-fe67965fc1). Likely waters (C-c601777a50) may add a Corps permit check. This adds some coordination time and cost.
Cites C-fe67965fc1, C-c601777a50
Supporting statements (2)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-c601777a50
Sugar Run and its tributaries are likely jurisdictional waters of the United States.
Quoted from page 2
Sugar Run and its tributaries are likely jurisdictional waters of the United States.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source consultant_memo · Claim type presence · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by AQ-01 · Filed under AQ-01, PE-03
C-fe67965fc1
An existing 138 kV transmission line crosses the eastern portion of the Project Area.
Quoted from page 1
An existing 138 kV transmission line crosses the eastern portion of the Project Area.
Brook Hollow Project Overview 2023-03-15 · DR-0001 · Page 1 · 2023-03-15
Source developer_document · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-01 · Filed under EN-01, PE-03
3 Permits and requirements
The requirements tied to the rows of this report, by level.
Engine 0.1.0, which made this run, wrote no timelines or citations of law.
Federal (2)
NEPA review (categorical exclusion, environmental assessment or EIS)
F-NEPA · Lead federal agency
	Applicability
	Conditional

	Instrument
	National Environmental Policy Act (42 U.S.C. 4321 et seq.)

	Trigger
	Federal nexus.

	Description
	Environmental review of major federal actions, such as federal land use, funding, loans or individual federal permits.

	As of the cut-off
	As of the cut-off: Fiscal Responsibility Act amended NEPA. (2023-06-03) Changed after the cut-off (not applied): CEQ's NEPA implementing regulations were rescinded. (2025-04-11)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-NEPA


Spill Prevention, Control and Countermeasure (SPCC) Plan
F-SPCC · U.S. Environmental Protection Agency
	Applicability
	Conditional

	Instrument
	Oil Pollution Prevention, 40 CFR Part 112

	Trigger
	Substation and inverter transformers holding oil above the threshold.

	Description
	Required where aggregate aboveground oil storage capacity exceeds 1,320 gallons (counting containers of 55 gallons or more, including oil-filled transformers) and a discharge could reach navigable waters.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-SPCC


State (3)
INDOT access and utility ROW permits and oversize/overweight load permits
S-07 · Indiana Department of Transportation (INDOT) and county highway department
	Applicability
	Conditional

	Instrument
	Road/ROW permits, oversize/overweight haul permits

	Trigger
	Access, crossings or hauling on state routes

	Description
	Needed for state-highway driveway access, utility crossings of state ROW, and delivery of heavy equipment such as main power transformers.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-07


Regulated drain crossing/encroachment approval and tile protection
S-08 · Indiana DNR / county Drainage Board / County Surveyor
	Applicability
	Conditional

	Instrument
	Indiana Drainage Code (IC 36-9-27); regulated drains

	Trigger
	Work within regulated drain easements or disturbing drainage tile

	Description
	Crossings or work near county regulated drains need Drainage Board approval. Agricultural tile disturbed by construction must be repaired.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-08


Construction Design Release for certain structures
S-09 · Indiana Department of Homeland Security (Fire Prevention and Building Safety Commission)
	Applicability
	Conditional

	Instrument
	Indiana Design Release / electrical code

	Trigger
	Construction of enclosed buildings of qualifying class

	Description
	Applies to qualifying buildings such as O&M or substation control buildings. Not typically needed for solar arrays themselves.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-09


Local (2)
ILP preceded by decommissioning bond
L-03 · Fixture County Plan Commission / Building Department
	Applicability
	Required

	Instrument
	Improvement Location Permit (ILP) and decommissioning bond

	Trigger
	Before construction

	Description
	The ordinance requires a decommissioning bond before issuance of the ILP. Building and electrical permits are likely part of the ILP process.

	As of the cut-off
	Ordinance as of 2023-04-02.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-81ccc0d11b

	In the permit matrix
	L-03


Local road use agreement and moratorium check (to be confirmed)
L-04 · Fixture County / township
	Applicability
	To be confirmed

	Instrument
	Road use and maintenance agreement; local moratorium check

	Trigger
	Use of county roads, including CR 400 N, for hauling

	Description
	The data room says nothing about road use agreements or moratoria. The township trustees took no action after the April 2023 meeting, and no moratorium is evidenced.

	As of the cut-off
	As of 2023-08-15 no moratorium is evidenced.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-cd028dc455

	In the permit matrix
	L-04


4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
Medium priority (1)
IR-09b3f986d4 · Medium priority
Provide the evidence of federal land, funding or permits for the project area, or confirm none exists.
	Missing evidence
	Evidence of federal land, funding or permits

	Consequence
	Other is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Identify line owner and crossing/encroachment terms; overlay line corridor on site layout.
Confirm Corps jurisdiction for Sugar Run and any Section 404/Section 106 federal nexus.
Check railroad, state route and county road crossings, regulated drains, and SPCC applicability once transformer oil volumes are known.
Agencies
EPA
USACE
Transmission line owner (to be identified)
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-15.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (2)
Wetland and Stream Delineation Report May2023 · DR-0005 · 2023-05-22 · page 2
Brook Hollow Project Overview 2023-03-15 · DR-0001 · 2023-03-15 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-15

	Engine version
	0.1.0

	Prompt version
	2026-10-02.1

	Rows pack
	rows.json sha256 d1df27b21f79b09d

	Federal pack
	federal.json sha256 aa17c41356542d46

	State pack
	none

	Local pack
	Not written by this engine

	Data room manifest
	6141b7dc1f8441489d39e4023d551e4c0021a37ce4f9ad157607d9096c58bfb5

	Audit chain
	valid (92 events)

	QA status
	PASS

	Rendered at
	2026-10-01T21:09:12+00:00

	Run record (annex)
	a03418c2562baa8a57b7c256ce665acd2c20e92d06e365604d162e9029f8fdd6

	Exporter
	Prism/room/exporter 1.4.0
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