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Flood report
Brook Hollow Solar
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
Mapped flood hazard in and around the study area: FEMA special flood hazard areas, meaning the 1% annual chance floodplain and the regulatory floodway, and other mapped flood-prone land.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-15

	Row in the matrix
	AQ-02 Floodplains


1 Finding
2  Impacts likely but may be easily resolved
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released

	Evidence state
	REPORTED · desktop, consultant or developer record


The assessor's comments
FEMA FIRM panel 18999C0150D maps Zone A (100-year floodplain) along Sugar Run. The mapped floodplain is approximately 300 feet wide through the center of the site. No FIRM panel or floodplain administrator correspondence is in the data room.
2 What the record shows
The five inputs
Present: yes
FEMA FIRM panel 18999C0150D maps Zone A (100-year floodplain) along Sugar Run (C-265b2e4481); the mapped floodplain runs through the site center (C-1ebafa9bbc).
Cites C-265b2e4481, C-1ebafa9bbc
Extent: core
Mapped floodplain is about 300 feet wide through the center of the site (C-1ebafa9bbc), following Sugar Run, which bisects the Project Area north to south (C-b2682b602a).
Cites C-1ebafa9bbc, C-b2682b602a
Avoidable: yes
A band about 300 feet wide (C-1ebafa9bbc) within a 1,356-acre project is a small share of buildable land; arrays and equipment can be sited outside it, with only collection lines or roads crossing, the consultant recommending HDD for Sugar Run crossings (C-5a22a97656).
Cites C-1ebafa9bbc, C-5a22a97656
Pathway: standard
Zone A is a mapped flood hazard area, so a local floodplain development permit (F-NFIP) applies to any crossings or work (C-265b2e4481). No floodway is documented, so an individual no-rise pathway is not established. The state floodway permit S-04 is unverified.
Cites C-265b2e4481
Impact likely: yes
The floodplain crosses the center of the site (C-1ebafa9bbc), and a typical build needs road and collection-line crossings of Sugar Run (C-b2682b602a, C-5a22a97656), so permitting and crossing work are likely even if arrays avoid it.
Cites C-1ebafa9bbc, C-b2682b602a, C-5a22a97656
Supporting statements (4)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-1ebafa9bbc
The mapped floodplain is approximately 300 feet wide through the center of the site.
Quoted from page 4
The mapped floodplain is approximately 300 feet wide through the center of the site.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 4 · 2023-05-22
Source map_or_figure · Claim type extent · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-265b2e4481
FEMA FIRM panel 18999C0150D maps Zone A (100-year floodplain) along Sugar Run.
Quoted from page 4
FEMA FIRM panel 18999C0150D maps Zone A (100-year floodplain) along Sugar Run.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 4 · 2023-05-22
Source map_or_figure · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-5a22a97656
Consultant recommends avoiding all delineated features and using horizontal directional drilling for collection line crossings of Sugar Run.
Quoted from page 2
We recommend avoidance of all delineated features; collection line crossings of Sugar Run
should use horizontal directional drilling (HDD).
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Cited by AQ-01 · Filed under AQ-01
C-b2682b602a
Sugar Run, a perennial stream, bisects the center of the Project Area from north to south.
Quoted from page 2
Sugar Run, a perennial stream, bisects the center of the Project Area from north to south.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by AQ-01, EC-02 · Filed under AQ-01
3 Permits and requirements
The requirements tied to the rows of this report, by level.
Engine 0.1.0, which made this run, wrote no timelines or citations of law.
Federal (1)
Floodplain development permit
F-NFIP · Local floodplain administrator (NFIP community), FEMA
	Applicability
	Conditional

	Instrument
	National Flood Insurance Program (44 CFR Parts 59-60) and local flood damage prevention ordinance

	Trigger
	Equipment, fill or structures in a mapped flood hazard area.

	Description
	Development within a FEMA Special Flood Hazard Area requires a local floodplain development permit; floodway encroachment needs a no-rise analysis.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-NFIP


State (1)
Construction in a Floodway permit
S-04 · Indiana Department of Natural Resources (DNR) Division of Water
	Applicability
	Conditional

	Instrument
	Flood Control Act permit (IC 14-28-1)

	Trigger
	Any work in a mapped floodway or on a stream with 1+ sq mi drainage area

	Description
	Required for construction in a designated floodway of streams with drainage area of 1 square mile or more, e.g. Sugar Run crossings, collection lines, or fencing.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	Basis
	C-c601777a50

	In the permit matrix
	S-04


4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
Medium priority (2)
IR-ecff39a0bd · Medium priority
Provide the fema firm panel or flood-zone determination for the project area, or confirm none exists.
	Missing evidence
	FEMA FIRM panel or flood-zone determination

	Consequence
	Floodplains is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


IR-89f116c01d · Medium priority
Provide the local floodplain administrator correspondence or ordinance for the project area, or confirm none exists.
	Missing evidence
	Local floodplain administrator correspondence or ordinance

	Consequence
	Floodplains is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Obtain FIRM panel and confirm whether a regulatory floodway is mapped.
Site arrays and equipment outside Zone A; use HDD for Sugar Run crossings.
Consult local floodplain administrator and Indiana DNR on permits.
Agencies
FEMA
Local floodplain administrator (NFIP community)
Indiana DNR Division of Water
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-15.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (1)
Wetland and Stream Delineation Report May2023 · DR-0005 · 2023-05-22 · pages 2, 4
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-15

	Engine version
	0.1.0

	Prompt version
	2026-10-02.1

	Rows pack
	rows.json sha256 d1df27b21f79b09d

	Federal pack
	federal.json sha256 aa17c41356542d46

	State pack
	none

	Local pack
	Not written by this engine

	Data room manifest
	6141b7dc1f8441489d39e4023d551e4c0021a37ce4f9ad157607d9096c58bfb5

	Audit chain
	valid (92 events)

	QA status
	PASS

	Rendered at
	2026-10-01T21:09:12+00:00

	Run record (annex)
	a03418c2562baa8a57b7c256ce665acd2c20e92d06e365604d162e9029f8fdd6

	Exporter
	Prism/room/exporter 1.4.0
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