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Local zoning and permitting report
Brook Hollow Solar
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
The approvals the project needs: zoning and other local land-use permits, state siting and state permits, and other approvals such as a federal nexus, crossing permits or spill planning.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-15

	Rows in the matrix
	PE-01 Local Zoning & Permitting, PE-02 State Jurisdiction, PE-03 Other


1 Finding
PE-01 Local Zoning & Permitting
3  Resource is present, likely difficult to address
	The rule
	Code computed the rating from the assessor's inputs:
extent=core, avoidable=partly -> 3
Set by the rule

	Decision
	Released

	Evidence state
	VERIFIED · field study or agency determination


The assessor's comments
Parcels are zoned A-1 Agricultural. Special exception is granted by the Board of Zoning Appeals following a public hearing. Ordinance requires a 250-foot setback from non-participating residences and a decommissioning bond before the improvement location permit. Residents along CR 400 N voiced opposition at a township meeting. Moratorium and road use status unconfirmed.
PE-02 State Jurisdiction
2  Impacts likely but may be easily resolved
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released with flags

	The engine's reasons
	Agencies not in the register or the evidence: IURC (conditional)
Category 2 is plausible from the applies-level NPDES requirement. The assessment is weakened by inconsistent handling of S-02 (labeled data-room evidenced but described as having no quote), an avoidability call made without delineation evidence, and an extent call that rests on professional judgment.

	Evidence state
	INFERRED · reasoned from several records


The assessor's comments
No state siting application, agency correspondence, or stormwater permit/SWPPP is included in the data room. Construction stormwater general permit coverage applies. An IDEM 401 WQC/isolated wetland permit is likely if fill or discharge occurs in waters or isolated wetlands. IURC CPCN applicability is unconfirmed.
PE-03 Other
2  Impacts likely but may be easily resolved
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released with flags

	The engine's reasons
	Agencies not in the register or the evidence: EPA, USACE, Transmission line owner (to be identified)

	Evidence state
	INFERRED · reasoned from several records


The assessor's comments
An existing 138 kV transmission line crosses the eastern portion of the Project Area; crossing or encroachment coordination is likely. Line ownership and terms are not documented. No federal land, funding or permit is documented in the data room. Sugar Run and tributaries are likely jurisdictional waters.
2 What the record shows
PE-01 Local Zoning & Permitting
The five inputs
Present: yes
Parcels are zoned A-1 Agricultural (C-d8361ea2dc) and a special exception is granted by the Board of Zoning Appeals following a public hearing (C-318952bc4a). Candidate requirements L-01, L-02 and L-03 apply; the 250-foot setback and decommissioning bond are documented (C-2ad119167d, C-81ccc0d11b).
Cites C-d8361ea2dc, C-318952bc4a, C-2ad119167d, C-81ccc0d11b
Extent: core
Zoning, special exception and ordinance requirements govern the whole project on A-1 parcels (C-d8361ea2dc, C-318952bc4a).
Cites C-d8361ea2dc, C-318952bc4a
Avoidable: partly
A special exception after a public hearing is judged discretionary but usually granted (inference; C-318952bc4a only shows a hearing occurs). Opposition at the township level (views, property values; 60-signature petition to trustees) is documented, but it was directed to trustees, not the BZA, and trustees took no action (C-17067c687e, C-9219b5c2a9, C-cd028dc455). The 500 ft setback request is undated (C-fd8c52be70). Denial is not shown to be realistic; moratorium status is unknown, not absent.
Cites C-318952bc4a, C-17067c687e, C-9219b5c2a9, C-cd028dc455, C-fd8c52be70
Pathway: individual
Professional judgment: a special exception following a public hearing (C-318952bc4a), with local resident opposition and a petition at township level (C-17067c687e, C-9219b5c2a9), is treated as a hearing-based discretionary approval rather than routine administrative; 'contested' is inferred. Trustees took no action (C-cd028dc455). Whether a moratorium applies is unknown, not documented either way (L-04 unconfirmed).
Cites C-318952bc4a, C-17067c687e, C-9219b5c2a9, C-cd028dc455
Impact likely: yes
Local approvals are required: special exception hearing, 250-foot setback compliance, and decommissioning bond before the improvement location permit (C-318952bc4a, C-2ad119167d, C-81ccc0d11b). Schedule and condition exposure; resident requests for larger setbacks and screening could add conditions (C-fd8c52be70, undated).
Cites C-318952bc4a, C-2ad119167d, C-81ccc0d11b, C-fd8c52be70
Supporting statements (8)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-17067c687e
Several residents along CR 400 N voiced opposition at the April 18 township meeting, mainly about views and property values.
Quoted from page 1
Several residents along CR 400 N voiced opposition at the April 18 township meeting, mainly about views and property values.
Email: RE: Township meeting recap · DR-0010 · Page 1 · 2023-04-19
Source correspondence · Claim type stakeholder · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by CO-02, VI-01 · Filed under CO-02, VI-01
C-2ad119167d
The Fixture County Solar Ordinance requires a 250-foot setback from non-participating residences.
Quoted from page 1
The Fixture County Solar Ordinance requires a 250-foot setback from non-participating residences
Fixture County Zoning Verification Letter 2023-04-02 · DR-0007 · Page 1 · 2023-04-02
Source public_record · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by CO-02, VI-01 · Filed under CO-02, PE-01, VI-01
C-318952bc4a
The special exception is granted by the Board of Zoning Appeals following a public hearing.
Quoted from page 1
granted by the Board of Zoning Appeals following a public hearing.
Fixture County Zoning Verification Letter 2023-04-02 · DR-0007 · Page 1 · 2023-04-02
Source agency_determination · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by CO-02 · Filed under CO-02, PE-01
C-81ccc0d11b
The ordinance requires a decommissioning bond prior to issuance of an improvement location permit.
Quoted from page 1
a decommissioning bond prior to issuance of an improvement location permit.
Fixture County Zoning Verification Letter 2023-04-02 · DR-0007 · Page 1 · 2023-04-02
Source public_record · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-9219b5c2a9
A petition with 60 signatures was submitted to the township trustees.
Quoted from page 1
A petition with 60 signatures was submitted to the township trustees.
Email: RE: Township meeting recap · DR-0010 · Page 1 · 2023-04-19
Source correspondence · Claim type stakeholder · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by CO-02 · Filed under CO-02
C-cd028dc455
The township trustees did not take any action following the meeting.
Quoted from page 1
The trustees did not take any action.
Email: RE: Township meeting recap · DR-0010 · Page 1 · 2023-04-19
Source correspondence · Claim type other · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Cited by CO-02 · Filed under CO-02, PE-01
C-d8361ea2dc
The subject parcels are zoned A-1 Agricultural.
Quoted from page 1
The subject parcels are zoned A-1 Agricultural.
Fixture County Zoning Verification Letter 2023-04-02 · DR-0007 · Page 1 · 2023-04-02
Source agency_determination · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-03 · Filed under EN-03, PE-01
C-fd8c52be70
Residents asked for 500 ft setbacks and vegetative screening along CR 400 N at a township meeting.
Quoted from page 1
residents asked for 500 ft setbacks and vegetative screening along CR 400 N.
meeting notes · DR-0012 · Page 1 · Undated
Source correspondence · Claim type stakeholder · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by CO-02, VI-01 · Filed under CO-02, PE-01, VI-01
PE-02 State Jurisdiction
The five inputs
Present: yes
No data-room claims exist for this row. Candidate requirement F-CWA402 (NPDES construction stormwater coverage and SWPPP, applies, PACK_PENDING_QUALIFIED_REVIEW) supports state approvals being required; in Indiana IDEM administers it. S-02 (IDEM 401 WQC/isolated wetland permit, likely, DATA_ROOM_EVIDENCED) is also listed as a candidate requirement, but no quote is provided to support the Sugar Run reference. S-03 is model knowledge only and is not relied on alone.
Cites no claim.
Extent: core
Construction stormwater coverage applies to every utility-scale project and governs the project as a whole. The disturbed acreage is not documented (1,356 acres is total project area), but the permit still covers the whole project under the common plan of development. This is a professional judgment.
Cites no claim.
Avoidable: yes
Construction stormwater coverage is a general permit and is routinely obtainable. Any S-02 permit is triggered only by fill or discharge, and siting can avoid that. Ownership and offtake structure are not documented, so IURC CPCN applicability (S-01, unverified, conditional) is unknown and not assumed either way.
Cites no claim.
Pathway: standard
The established requirement is a general permit (NPDES construction stormwater) with routine IDEM review. No evidence shows a full siting certificate proceeding or a statutory bar. The CPCN question is open and is handled as a next step.
Cites no claim.
Impact likely: yes
State approvals are required. Stormwater NOI/SWPPP preparation and possible IDEM water quality review add cost and schedule for a typical utility-scale build.
Cites no claim.
Supporting statements (0)
The row cites no claim.
PE-03 Other
The five inputs
Present: yes
C-fe67965fc1 documents an existing 138 kV transmission line crossing the eastern Project Area, so utility crossing or encroachment coordination is a reasonable expectation for a solar build. F-SPCC is conditional on oil volume above the threshold, which is not documented; SPCC applicability is therefore a possibility, not a documented need. No federal land, funding or permit is documented. C-c601777a50 (likely jurisdictional waters) points to a possible Section 404 nexus, but whether impacts occur is undetermined. L-03 (applies) is a local approval addressed in the local zoning row.
Cites C-fe67965fc1, C-c601777a50
Extent: unknown
C-fe67965fc1 places the line in the eastern portion but does not show how much of the 1,356-acre site it affects, and no layout is documented. No project-wide federal nexus is documented, so NEPA is not shown to cover the whole project. Extent cannot be established from the evidence.
Cites C-fe67965fc1
Avoidable: yes
Line ownership and crossing terms are not documented. As a professional judgment, utility crossing agreements and SPCC plans are typically routine, and no evidence of a realistic denial exists. A federal nexus is not documented, so no discretionary approval is shown.
Cites C-fe67965fc1
Pathway: standard
Judgment: a crossing or encroachment agreement with the line owner (owner undocumented) and a possible SPCC plan follow standard processes. No federal nexus requiring an EA or EIS is documented. A Section 404 nationwide permit tied to C-c601777a50 would also be standard if wetland impacts occur.
Cites C-fe67965fc1, C-c601777a50
Impact likely: yes
Judgment, not documented layout: collection-line, access road and fence work on a site crossed by an existing 138 kV line will typically need crossing or encroachment coordination (C-fe67965fc1). Likely waters (C-c601777a50) may add a Corps permit check. This adds some coordination time and cost.
Cites C-fe67965fc1, C-c601777a50
Supporting statements (2)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-c601777a50
Sugar Run and its tributaries are likely jurisdictional waters of the United States.
Quoted from page 2
Sugar Run and its tributaries are likely jurisdictional waters of the United States.
Wetland and Stream Delineation Report May2023 · DR-0005 · Page 2 · 2023-05-22
Source consultant_memo · Claim type presence · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by AQ-01 · Filed under AQ-01, PE-03
C-fe67965fc1
An existing 138 kV transmission line crosses the eastern portion of the Project Area.
Quoted from page 1
An existing 138 kV transmission line crosses the eastern portion of the Project Area.
Brook Hollow Project Overview 2023-03-15 · DR-0001 · Page 1 · 2023-03-15
Source developer_document · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-01 · Filed under EN-01, PE-03
3 Permits and requirements
The requirements tied to the rows of this report, by level.
Engine 0.1.0, which made this run, wrote no timelines or citations of law.
Federal (3)
NPDES Construction Stormwater General Permit coverage and SWPPP
F-CWA402 · State NPDES permitting authority (EPA where not delegated)
	Applicability
	Required

	Instrument
	Clean Water Act Section 402 (33 U.S.C. 1342); 40 CFR 122.26

	Trigger
	Construction disturbing one acre or more, or part of a larger common plan of development.

	Description
	Coverage under the construction stormwater general permit with a Stormwater Pollution Prevention Plan for land disturbance of one acre or more.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-CWA402


NEPA review (categorical exclusion, environmental assessment or EIS)
F-NEPA · Lead federal agency
	Applicability
	Conditional

	Instrument
	National Environmental Policy Act (42 U.S.C. 4321 et seq.)

	Trigger
	Federal nexus.

	Description
	Environmental review of major federal actions, such as federal land use, funding, loans or individual federal permits.

	As of the cut-off
	As of the cut-off: Fiscal Responsibility Act amended NEPA. (2023-06-03) Changed after the cut-off (not applied): CEQ's NEPA implementing regulations were rescinded. (2025-04-11)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-NEPA


Spill Prevention, Control and Countermeasure (SPCC) Plan
F-SPCC · U.S. Environmental Protection Agency
	Applicability
	Conditional

	Instrument
	Oil Pollution Prevention, 40 CFR Part 112

	Trigger
	Substation and inverter transformers holding oil above the threshold.

	Description
	Required where aggregate aboveground oil storage capacity exceeds 1,320 gallons (counting containers of 55 gallons or more, including oil-filled transformers) and a discharge could reach navigable waters.

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-SPCC


State (9)
No state siting certificate for 120 MWac merchant solar (IURC CPCN not required)
S-01 · Indiana Utility Regulatory Commission (IURC)
	Applicability
	Conditional

	Instrument
	Certificate of Public Convenience and Necessity / siting

	Trigger
	Only if project is utility-owned or the utility seeks IURC approval of PPA/ownership

	Description
	Indiana has no state siting permit for private solar; siting is local. IURC jurisdiction applies only to regulated utilities (IC 8-1-8.5 CPCN for utility-owned generation or PPA approval) and would be triggered only if Prairie Electric owns or seeks approval for the project.

	As of the cut-off
	As of 2023-08-15 Indiana had no state solar siting permit; local control prevails (the 2023 legislative session considered but did not enact a state siting override for solar; IC 36-7-4-1109 on local wind/solar ordinances was later amended in 2024-2025 efforts). Check later changes.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-01


401 WQC and isolated wetland permit
S-02 · Indiana Department of Environmental Management (IDEM)
	Applicability
	Likely

	Instrument
	Section 401 Water Quality Certification / State Isolated Wetland permit (IC 13-18-22)

	Trigger
	Fill or discharge in Sugar Run/tributaries or isolated wetlands

	Description
	Sugar Run and tributaries are likely jurisdictional waters, so a 401 WQC is required with any federal Section 404 permit. Isolated state-regulated wetlands and waters not covered federally need an IDEM isolated wetland permit if impacted.

	As of the cut-off
	As of 2023-08-15, after Sackett v. EPA (May 2023), federal jurisdiction narrowed, making state isolated wetland permitting more important. Indiana SEA 389 (2021) deregulated Class I and some Class II isolated wetlands.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-c601777a50

	In the permit matrix
	S-02


Notice of Intent and Construction Stormwater Pollution Prevention Plan
S-03 · IDEM
	Applicability
	Required

	Instrument
	Construction Stormwater General Permit (327 IAC 15-5, Rule 5)

	Trigger
	Land disturbance of 1 acre or more

	Description
	Land disturbance of one acre or more requires Rule 5 NOI submitted to IDEM, with the SWPPP reviewed by the county SWCD or MS4. This project disturbs well over one acre.

	As of the cut-off
	Rule 5 as of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-03


Construction in a Floodway permit
S-04 · Indiana Department of Natural Resources (DNR) Division of Water
	Applicability
	Conditional

	Instrument
	Flood Control Act permit (IC 14-28-1)

	Trigger
	Any work in a mapped floodway or on a stream with 1+ sq mi drainage area

	Description
	Required for construction in a designated floodway of streams with drainage area of 1 square mile or more, e.g. Sugar Run crossings, collection lines, or fencing.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	Basis
	C-c601777a50

	In the permit matrix
	S-04


Environmental review request for state endangered and threatened species
S-05 · Indiana DNR Division of Fish & Wildlife / Nature Preserves; USFWS Bloomington field office
	Applicability
	Likely

	Instrument
	Natural Heritage Database review and state-listed species review (IC 14-31, 312 IAC 9)

	Trigger
	Always for screening; tree clearing and stream work raise risk

	Description
	Request a DNR Environmental Review for state-listed species and natural heritage. Indiana bat and northern long-eared bat tree clearing windows are commonly recommended.

	As of the cut-off
	As of 2023-08-15. NLEB was reclassified as federally endangered effective March 2023.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-05


SHPO review; Section 106 consultation if a federal nexus exists; DNR Archaeology Plan/Permit for state-land or discovered human remains
S-06 · Indiana DNR Division of Historic Preservation and Archaeology (SHPO)
	Applicability
	Conditional

	Instrument
	IC 14-21-1 Historic Preservation and Archaeology Act, state permit

	Trigger
	Federal nexus (e.g. 404 permit) or discovery of burials/archaeological artifacts

	Description
	No general state review for private land without a state or federal nexus, but SHPO consultation is triggered through federal permits. Inadvertent discovery of human remains or burials requires DNR notification under IC 14-21-1.

	As of the cut-off
	As of 2023-08-15. Federal nexus is missing from the project facts.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-06


INDOT access and utility ROW permits and oversize/overweight load permits
S-07 · Indiana Department of Transportation (INDOT) and county highway department
	Applicability
	Conditional

	Instrument
	Road/ROW permits, oversize/overweight haul permits

	Trigger
	Access, crossings or hauling on state routes

	Description
	Needed for state-highway driveway access, utility crossings of state ROW, and delivery of heavy equipment such as main power transformers.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-07


Regulated drain crossing/encroachment approval and tile protection
S-08 · Indiana DNR / county Drainage Board / County Surveyor
	Applicability
	Conditional

	Instrument
	Indiana Drainage Code (IC 36-9-27); regulated drains

	Trigger
	Work within regulated drain easements or disturbing drainage tile

	Description
	Crossings or work near county regulated drains need Drainage Board approval. Agricultural tile disturbed by construction must be repaired.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-08


Construction Design Release for certain structures
S-09 · Indiana Department of Homeland Security (Fire Prevention and Building Safety Commission)
	Applicability
	Conditional

	Instrument
	Indiana Design Release / electrical code

	Trigger
	Construction of enclosed buildings of qualifying class

	Description
	Applies to qualifying buildings such as O&M or substation control buildings. Not typically needed for solar arrays themselves.

	As of the cut-off
	As of 2023-08-15.

	Verification
	MODEL_KNOWLEDGE_UNVERIFIED

	Source
	model:jurisdiction

	In the permit matrix
	S-09


Local (4)
Special exception for commercial solar energy system following public hearing
L-01 · Fixture County Board of Zoning Appeals
	Applicability
	Required

	Instrument
	Fixture County Solar Ordinance; A-1 zoning; special exception

	Trigger
	Commercial solar in A-1 district

	Description
	Parcels are zoned A-1 Agricultural, where commercial solar is allowed only by special exception from the BZA following a public hearing. Local opposition has been voiced, so the hearing is a key risk.

	As of the cut-off
	Ordinance as shown in the data-room records dated 2023-04-02. Later amendments are not known.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-d8361ea2dc, C-f716da1017, C-318952bc4a, C-17067c687e, C-9219b5c2a9

	In the permit matrix
	L-01


Compliance with 250-foot setback from non-participating residences
L-02 · Fixture County Solar Ordinance
	Applicability
	Required

	Instrument
	Setback and screening standards

	Trigger
	Site layout near non-participating residences, especially along CR 400 N

	Description
	The ordinance requires 250 ft from non-participating residences. Residents asked for 500 ft and screening along CR 400 N, which the BZA could impose as a condition of the special exception, but this request is not part of the ordinance.

	As of the cut-off
	Ordinance as of 2023-04-02. The 500 ft request is undated and non-binding.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-2ad119167d, C-fd8c52be70

	In the permit matrix
	L-02


ILP preceded by decommissioning bond
L-03 · Fixture County Plan Commission / Building Department
	Applicability
	Required

	Instrument
	Improvement Location Permit (ILP) and decommissioning bond

	Trigger
	Before construction

	Description
	The ordinance requires a decommissioning bond before issuance of the ILP. Building and electrical permits are likely part of the ILP process.

	As of the cut-off
	Ordinance as of 2023-04-02.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-81ccc0d11b

	In the permit matrix
	L-03


Local road use agreement and moratorium check (to be confirmed)
L-04 · Fixture County / township
	Applicability
	To be confirmed

	Instrument
	Road use and maintenance agreement; local moratorium check

	Trigger
	Use of county roads, including CR 400 N, for hauling

	Description
	The data room says nothing about road use agreements or moratoria. The township trustees took no action after the April 2023 meeting, and no moratorium is evidenced.

	As of the cut-off
	As of 2023-08-15 no moratorium is evidenced.

	Verification
	DATA_ROOM_EVIDENCED

	Source
	model:jurisdiction

	Basis
	C-cd028dc455

	In the permit matrix
	L-04


4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
High priority (1)
IR-f2153419ed · High priority
Provide the permitting plan or schedule for the project area, or confirm none exists.
	Row
	PE-01 Local Zoning & Permitting

	Missing evidence
	Permitting plan or schedule

	Consequence
	Local Zoning & Permitting is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


Medium priority (3)
IR-ee6010c685 · Medium priority
Provide the state siting application, docket record or agency correspondence for the project area, or confirm none exists.
	Row
	PE-02 State Jurisdiction

	Missing evidence
	State siting application, docket record or agency correspondence

	Consequence
	State Jurisdiction is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


IR-1a7896d177 · Medium priority
Provide the stormwater permit / swppp for the project area, or confirm none exists.
	Row
	PE-02 State Jurisdiction

	Missing evidence
	Stormwater permit / SWPPP

	Consequence
	State Jurisdiction is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


IR-09b3f986d4 · Medium priority
Provide the evidence of federal land, funding or permits for the project area, or confirm none exists.
	Row
	PE-03 Other

	Missing evidence
	Evidence of federal land, funding or permits

	Consequence
	Other is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
PE-01 Local Zoning & Permitting
Next steps
Engage county planning staff early; confirm BZA hearing date, special exception application and decommissioning bond amount.
Engage CR 400 N residents; evaluate larger setbacks and vegetative screening.
Confirm road use agreement requirements and whether any moratorium applies.
Agencies
Fixture County Board of Zoning Appeals
Fixture County Solar Ordinance
Fixture County Plan Commission / Building Department
Fixture County / township
PE-02 State Jurisdiction
Next steps
Confirm with IURC whether a CPCN is needed given ownership and offtake structure.
Plan IDEM stormwater NOI and SWPPP; 401/isolated wetland permit if fill is unavoidable.
Check mapped floodways and drainage areas for DNR floodway permit; submit DNR species screening; review INDOT access/hauling triggers.
Agencies
IDEM
Indiana DNR
IURC (conditional)
PE-03 Other
Next steps
Identify line owner and crossing/encroachment terms; overlay line corridor on site layout.
Confirm Corps jurisdiction for Sugar Run and any Section 404/Section 106 federal nexus.
Check railroad, state route and county road crossings, regulated drains, and SPCC applicability once transformer oil volumes are known.
Agencies
EPA
USACE
Transmission line owner (to be identified)
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-15.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (5)
Email: RE: Township meeting recap · DR-0010 · 2023-04-19 · page 1
Fixture County Zoning Verification Letter 2023-04-02 · DR-0007 · 2023-04-02 · page 1
meeting notes · DR-0012 · Undated · page 1
Wetland and Stream Delineation Report May2023 · DR-0005 · 2023-05-22 · page 2
Brook Hollow Project Overview 2023-03-15 · DR-0001 · 2023-03-15 · page 1
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