
Tamsin Ridge Solar and Storage · Archaeological Resources and Cemeteries: desk report
Archaeological Resources and Cemeteries: desk report
Tamsin Ridge Solar and Storage
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, CU-01 Archaeological Resources and Cemeteries, in the Cultural Resources section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-01

	Row in the matrix
	CU-01 Archaeological Resources and Cemeteries


1 Finding
2  Impacts likely but may be easily resolved
up to 3  Resource is present, likely difficult to address
The engine shows this rating as 2-3
	The rule
	Code computed the rating from the assessor's inputs:
impact_likely=yes -> 2
Set by the rule

	Decision
	Released with flags

	The engine's reasons
	Agencies not in the register or the evidence: OHPO

	Evidence state
	VERIFIED · field study or agency determination


The assessor's comments
Phase I survey recorded four new sites. Site 33-CR-0412 covers about 1.6 acres; draft layout places array rows over its north half, and a shift of about 150 feet would avoid it. Pettibone Family Cemetery lies 120 feet from arrays; unmarked graves may extend beyond its fence. No tribal consultation has taken place yet.
Worst case
If what is pending at the cut-off went badly, the same rule gives a higher rating.
	Scenario
	Radar confirms unmarked graves extending into planned array areas and 33-CR-0412 is found eligible, and a federal nexus triggers Section 106 adverse-effect resolution with data recovery or disinterment.

	Step still pending
	Ground-penetrating radar at the cemetery, SHPO review and Phase II testing of 33-CR-0412, plus tribal consultation

	Inputs in the worst case
	Extent peripheral · Avoidable partly · Pathway individual · Impact likely yes

	The rule on the worst case
	worst case: pathway=individual -> 3

	Claims that make it plausible
	C-75edf45e28, C-973edd2bcd, C-915bc9d3d5, C-f5449d6a0d, C-1134e16733


2 What the record shows
The five inputs
Present: yes
Phase I survey recorded four new sites (C-d3cd803c16), including 33-CR-0412, a lithic scatter with intact pit feature that may hold significant information (C-915bc9d3d5). Pettibone Family Cemetery adjoins Parcel 9 with possible unmarked graves outside the fence (C-973edd2bcd, C-75edf45e28, C-5aeb954b2a). Absence finding covers only three other sites needing no further work (C-3f34c70506); low potential in the mined part of the East Block (C-26b173c644) does not negate these.
Cites C-d3cd803c16, C-915bc9d3d5, C-973edd2bcd, C-75edf45e28, C-5aeb954b2a, C-3f34c70506, C-26b173c644
Extent: peripheral
Site 33-CR-0412 covers about 1.6 acres (C-257da2033f) and the 0.2-acre cemetery tract is excluded from the leased land (C-bb450a29a5), against 780 buildable acres. Both are small localized features; the cemetery is 120 feet from arrays (C-76863a3272).
Cites C-257da2033f, C-bb450a29a5, C-76863a3272
Avoidable: yes
Consultant states a shift of about 150 feet avoids 33-CR-0412 with its buffer (C-7041213fff); cemetery protection by buffer and fencing is recommended (C-1134e16733). Unmarked graves extent still unconfirmed but avoidance by layout is feasible.
Cites C-7041213fff, C-1134e16733
Pathway: standard
OPSB application must map cultural resources and describe avoidance, with SHPO-standard surveys submitted to SHPO (C-37779bcd55, C-4892410817; OH-HIST). Cemetery buffer and discovery plan follow SHPO guidance (OH-CEM, C-4d507135cc). Section 106 applies only if a federal nexus arises (C-f5449d6a0d), not established.
Cites C-37779bcd55, C-4892410817, C-4d507135cc, C-f5449d6a0d
Impact likely: yes
Draft layout places array rows over the north half of 33-CR-0412 (C-7041213fff), and arrays sit near the cemetery where unmarked graves may lie outside the fence (C-75edf45e28); grading and pile driving may affect them unless layout changes.
Cites C-7041213fff, C-75edf45e28
Supporting statements (16)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-1134e16733
Protect the cemetery with a 100-foot buffer, fenced during construction, after a ground-penetrating radar survey; moving any burial requires disinterment under ORC 517.23 and 517.24.
Quoted from page 3
Moving any burial would
require disinterment under ORC 517.23 and 517.24.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 3 · 2023-06-30
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
C-257da2033f
Site 33-CR-0412 covers about 1.6 acres and its pit feature contained fire-cracked rock and charcoal that could date the occupation.
Quoted from page 2
Site 33-CR-0412 covers about 1.6 acres.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 2 · 2023-06-30
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-26b173c644
Part of the East Block was disturbed by surface mining and reclamation, leaving low potential for intact sites there.
Quoted from page 1
part of the East Block was disturbed by surface mining and reclamation, which leaves low potential for intact sites there.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source desktop_study · Claim type study_finding · Polarity absence · Confidence high · Quote check exact, 100 of 100
C-37779bcd55
The OPSB application must map cultural resources and describe how impacts are avoided; the report will go to the SHPO with the application.
Quoted from page 3
The OPSB application must map cultural resources and describe how impacts are avoided.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 3 · 2023-06-30
Source consultant_memo · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under CU-01, PE-02
C-3f34c70506
Sites 33-CR-0413, 33-CR-0415 and 33-CR-0414 need no further work.
Quoted from page 1
none of the three needs further work.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source field_study · Claim type study_finding · Polarity absence · Confidence high · Quote check exact, 100 of 100
C-4892410817
Cultural resources surveys to SHPO standards must be submitted to the SHPO.
Quoted from page 1
Cultural resources surveys to SHPO standards, submitted to the SHPO.
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · Page 1 · 2023-03-28
Source agency_determination · Claim type regulatory · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Cited by CU-02 · Filed under CU-01, CU-02
C-4d507135cc
Adopt an unanticipated discovery plan: stop work within 100 feet and notify coroner, law enforcement and SHPO if remains or deposits are found.
Quoted from page 3
if human remains or archaeological deposits are found, stop work
 within 100 feet and notify the county coroner, law enforcement and the SHPO.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 3 · 2023-06-30
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence medium · Quote check exact, 100 of 100
C-5aeb954b2a
The Pettibone Family Cemetery, a small family burial ground, adjoins Parcel 9.
Quoted from page 1
the Pettibone Family Cemetery, a small family burial ground adjoining Parcel 9.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source desktop_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-7041213fff
The draft layout places array rows over the north half of site 33-CR-0412; a shift of about 150 feet would avoid it with the buffer.
Quoted from page 2
The draft layout places array rows over the north half of the site; a shift of about 150 feet
would avoid it with the buffer.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 2 · 2023-06-30
Source consultant_memo · Claim type constraint · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-75edf45e28
Two depressions outside the cemetery fence on the south side may be unmarked graves.
Quoted from page 2
Two depressions outside the fence on the south
side may be unmarked graves.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 2 · 2023-06-30
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-76863a3272
At KOP 4, Pettibone Family Cemetery, 120 feet from arrays, arrays are visible on three sides without screening.
Quoted from page 2
Pettibone Family Cemetery          120 feet            Arrays visible on three sides
Glare, Aviation and Visual Memo - Tamsin Ridge Solar and Storage Project · DR-0015 · Page 2 · 2023-04-25
Source consultant_memo · Claim type presence · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by VI-01 · Filed under CU-01, VI-01
C-915bc9d3d5
Site 33-CR-0412, a prehistoric lithic scatter with intact pit feature on a terrace above Sallow Creek, may hold significant information and should be avoided or evaluated by Phase II testing.
Quoted from page 1
may hold significant information and should be
avoided or evaluated by Phase II testing.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-973edd2bcd
The Pettibone Family Cemetery has six marked graves dated 1841 to 1886 on a 0.2-acre tract; unmarked graves may extend beyond its fence.
Quoted from page 1
Unmarked
graves may extend beyond its fence.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-bb450a29a5
A 0.2-acre Pettibone Family Cemetery tract adjoining Parcel 9 is excluded from the Land.
Quoted from page 3
The 0.2-acre Pettibone Family Cemetery tract adjoining Parcel 9 is excluded from the Land.
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 3 · 2023-04-18
Source public_record · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under CU-01, PE-05
C-d3cd803c16
Survey recorded four new archaeological sites.
Quoted from page 1
The survey recorded four new archaeological sites.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 1 · 2023-06-30
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-f5449d6a0d
If a Corps permit with pre-construction notification is needed, the Corps will consult the SHPO and tribes under Section 106; no tribal consultation has taken place yet.
Quoted from page 3
no tribal consultation has taken place yet.
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · Page 3 · 2023-06-30
Source consultant_memo · Claim type regulatory · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Cited by PE-03 · Filed under CU-01, PE-03
3 Permits and requirements
The requirements tied to the rows of this report, by level. Each quote from dated law is shown with its source, the version in force on the cut-off and the basis for it.
Federal (1)
Section 106 consultation
F-NHPA106 · Lead federal agency with the State Historic Preservation Office (and THPOs)
	Applicability
	Conditional

	Instrument
	National Historic Preservation Act Section 106 (54 U.S.C. 306108); 36 CFR Part 800

	Trigger
	Federal nexus, for example an individual Section 404 permit or federal funding.

	Description
	A federal undertaking (federal permit, funding, license or land) must take into account effects on historic properties.

	Typical timeline
	SHPO/THPO review: if it does not respond within 30 days of receiving a request for review of a finding or determination, the agency official may proceed to the next step or consult the Advisory Council (36 CFR 800.3(c)(4)). Under a Corps nationwide permit, an activity that may have the potential to cause effects to listed or eligible historic properties is not authorized until the Section 106 requirements have been satisfied (general condition 20(a)). Typical: 2 to 4 months for a no-adverse-effect finding once surveys are complete and 6 to 12 months or more if an adverse effect needs a memorandum of agreement (basis: practice, not stated in the sources).

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-NHPA106


Legal basis: 3 quotes from dated law
Quoted from the law, page 1
Undertaking means a project, activity, or program funded in whole or in part under the direct or indirect jurisdiction of a Federal agency, including those carried out by or on behalf of a Federal agency; those carried out with Federal financial assistance; and those requiring a Federal permit, license or approval.
Source 36CFR800 · page 1 · version 2023-08-01
Cited for requirement and trigger (federal nexus)
In force from 2016-12-13 to 2026-10-07
eCFR versioner: 36 CFR part 800, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-12-13
May be cited on the cut-off date.
Quoted from the law, page 126
No activity is authorized under any NWP which may have the potential to cause effects to properties listed, or eligible for listing, in the National Register of Historic Places until the requirements of Section 106 of the National Historic Preservation Act (NHPA) have been satisfied.
Source 86FR2744 · page 126 · version 2021-01-13
Cited for trigger and timeline: Corps nationwide permit waits for Section 106
May be cited on the cut-off date.
Quoted from the law, page 1
If the SHPO/THPO fails to respond within 30 days of receipt of a request for review of a finding or determination, the agency official may either proceed to the next step in the process based on the finding or determination or consult with the Council in lieu of the SHPO/THPO.
Source 36CFR800 · page 1 · version 2023-08-01
Cited for timeline: SHPO/THPO response period
In force from 2016-12-13 to 2026-10-07
eCFR versioner: 36 CFR part 800, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-12-13
May be cited on the cut-off date.
State (2)
Cultural and archaeological resources information in the OPSB application, supported by SHPO-standard archaeology and history/architecture surveys and SHPO review
OH-HIST · Ohio Power Siting Board (OPSB) for the application content; Ohio History Connection, State Historic Preservation Office (SHPO), for survey standards and review
	Applicability
	Required

	Instrument
	OAC 4906-4-08(D) (effective 2018-04-26); ORC 149.53; SHPO Archaeology Guidelines (2022) and Guidelines for Conducting History/Architecture Surveys in Ohio (2014); National Historic Preservation Act Section 106 where a federal permit or approval applies

	Trigger
	An OPSB certificate application for a generating facility under OAC Chapter 4906-4 must include cultural and archaeological resources information, and SHPO review follows where a federal permit or approval (Section 106) or a state agency (ORC 149.53) is involved.

	Description
	An OPSB certificate application for a generating facility must map registered landmarks of historic, religious, archaeological or other cultural significance within ten miles of the project area, evaluate the facility's impact on them and describe plans to avoid or mitigate adverse impact (OAC 4906-4-08(D)). SHPO sets the survey standards it reviews: its archaeology guidelines prescribe report formats, and its history/architecture guidelines require a qualified principal investigator for compliance surveys. Section 106 review, in which SHPO takes part, is a routine part of planning for projects with federal funding, permits, licenses or approvals. ORC 149.53 provides, whenever practical, for archaeological and historic survey in planning, including before work on a public improvement begins; SHPO says there is no formal consultation process under it, though its phased approach is typically followed, and the sources do not say whether it reaches a private facility certificated by the OPSB.

	Typical timeline
	Under Section 106 the regulations give SHPO thirty days to respond to submissions that meet 36 CFR 800.11, and incomplete submissions may need further information and analysis (SHPO form instructions). The sources state no period for comment under ORC 149.53, for which SHPO says there is no formal process.

	Version of the law on the cut-off
	As in force from 2023-08-01 (the library text)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:oh.json

	In the permit matrix
	OH-HIST


Legal basis: 8 quotes from dated law
Quoted from the law, page 29
(1) Landmark mapping. The applicant shall indicate, on a map of at least 1:24,000 scale, any formally adopted land and water recreation areas, recreational trails, scenic rivers, scenic routes or byways, and registered landmarks of historic, religious, archaeological, scenic, natural, or other cultural significance within ten miles of the project area.
Source OAC 4906 4 OPSB generation facility applications · page 29 · version 2023-08-01
In force from 2018-04-26 to 2024-05-29, section 4906-4-08
4906-4-08: version effective 2018-04-26; first change after it 2024-05-30 (OPSB Case 21-902-GE-BRO (determination 2023-07-20)), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 29
(2) Impacts on landmarks. The applicant shall provide an evaluation of the impact of the proposed facility on the preservation and continued meaningfulness of these landmarks and describe plans to avoid or mitigate any adverse impact.
Source OAC 4906 4 OPSB generation facility applications · page 29 · version 2023-08-01
In force from 2018-04-26 to 2024-05-29, section 4906-4-08
4906-4-08: version effective 2018-04-26; first change after it 2024-05-30 (OPSB Case 21-902-GE-BRO (determination 2023-07-20)), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 3
and for such purposes shall, whenever practical, by contract or otherwise provide for archaeological and historic survey and salvage work during the planning phases, before work on a public improvement begins or at other appropriate times;
Source ORC 149.51 to 149.55 historic preservation · page 3 · version 2023-08-01
In force from 2015-09-29 to 2026-10-03, section 149.53
149.53: version effective 2015-09-29, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 5
There is no formal process for consulting with SHPO under Ohio Revised Code (ORC) 149.53. However, the phased approach indicated above is typically followed.
Source OHC SHPO archaeology guidelines section fieldwork · page 5 · version 2023-05-31
May be cited on the cut-off date.
Quoted from the law, page 4
The following report formats are required for all archaeology undertakings reviewed by the State Historic Preservation Office (SHPO) pursuant to 36 CFR Part 800, regulations implementing Section 106 of the National Historic Preservation Act; and Ohio Revised Code (ORC) section 149.53, Archaeological and Historic Survey and Salvage Work.
Source OHC SHPO archaeology guidelines section report formats · page 4 · version 2022-11
May be cited on the cut-off date.
Quoted from the law, page 11
All surveys under taken for compliance projects and through Certified Local Governments (CLG s) Grants and History Fund Grants must be carried out under the professional direction of a Principal Investigator that meets the established professional qualifications set forth in the Secretary of the Interior’s Standards for Archeology and Historic Preservation for a Historian, Architectural Historian, or Historic Preservationist.
Source OHC SHPO guidelines for conducting history architecture surveys · page 11 · version 2014-11
May be cited on the cut-off date.
Quoted from the law, page 1
Section 106 is a routine part of the planning process for projects that receive federal funding, permits, licenses, or approvals, to ensure that preservation standards are factored into a project before work is authorized to begin.
Source OHC SHPO about section 106 page · page 1 · version 2023-08-01
May be cited on the cut-off date.
Quoted from the law, page 1
Following our review of the Project Summary Form and its associated documentation, SHPO may request additional information to help us understand your assessment of the project’s effect. The regulations give us thirty days to respond to project submissions that meet all the requirements found at 36 CFR 800.11. Incomplete submissions may require the preparation of additional information and analysis.
Source OHC SHPO section 106 project summary form instructions · page 1 · version 2022-06-21
May be cited on the cut-off date.
Avoidance of cemeteries and burial places (SHPO guidance); disinterment under ORC 517.23 and 517.24 if remains must be moved; stop work and notify if human remains are found
OH-CEM · Ohio History Connection, State Historic Preservation Office (SHPO), for burial-place guidance; cemetery officers and the court (disinterment); Ohio Department of Commerce, Division of Real Estate (cemetery registration)
	Applicability
	Conditional

	Instrument
	ORC 517.21 to 517.24; ORC Chapter 4767; ORC 2927.11; SHPO Archaeology Guidelines, Cemeteries, Burial Mounds, and Other Burial Places (November 2022)

	Trigger
	A cemetery, burial mound or other place of burial is known or suspected on or next to the project area, or human remains are found during survey or construction.

	Description
	The State Historic Preservation Office (SHPO) recommends preservation in place, with a 100-foot buffer shown on plans and fenced during construction; if 100 feet is not possible, geophysical survey and SHPO consultation set the avoidance area. Moving remains means disinterment. After an application is filed with the cemetery and costs are paid, it must follow within thirty days, subject to the statute's exceptions (ORC 517.23); a person not qualified to apply may obtain a court order (ORC 517.24(B)). Trustees or directors may order an abandoned cemetery discontinued and its remains removed (ORC 517.21). The sources do not say how these procedures apply to an isolated burial on private land. Purposely damaging a cemetery or Indian mound or earthwork without privilege is prohibited (ORC 2927.11). Cemetery registration (ORC 4767.02 to 4767.04) excludes family cemeteries and those with no interments in 25 years, so records may omit burial grounds.

	Typical timeline
	Disinterment: within thirty days after an application is filed with the cemetery and costs are paid, subject to the statute's exceptions (ORC 517.23(A)(1)). On an inadvertent discovery, all ground-disturbing activity within a 150-foot radius of the burial place must cease, and the discovery be reported to the county medical examiner or coroner, local law enforcement, the applicant, the landowner and SHPO (SHPO guidance).

	Version of the law on the cut-off
	ORC 517.23 and 517.24 as effective 2023-04-03 (the library text)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:oh.json

	In the permit matrix
	OH-CEM


Legal basis: 8 quotes from dated law
Quoted from the law, page 1
the board, trustees, or directors may order that the abandoned cemetery or the cemetery whose further use for burial purposes is believed to be detrimental to the public welfare or health be discontinued and provide for the removal of all remains buried in that cemetery,
Source ORC 517 2927.11 4767 1721 cemeteries · page 1 · version 2023-08-01
In force from 1995-11-24 to 2026-10-03, section 517.21
517.21: version effective 1995-11-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 3
shall disinter or grant permission to disinter any remains buried in the cemetery in either of the following circumstances: (1) Within thirty days after an application for disinterment is filed with the cemetery in accordance with division (A) of section 517.24 of the Revised Code and payment of the reasonable costs and expense of disinterment is made
Source ORC 517 2927.11 4767 1721 cemeteries · page 3 · version 2023-08-01
In force from 2023-04-03 to 2024-10-23, section 517.23
517.23: version effective 2023-04-03; first change after it 2024-10-24 (H.B. 301, 135th GA), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 6
(B)(1) A person who is eighteen years of age or older and of sound mind and who is not qualified to file an application to disinter pursuant to division (A)(1) of section 517.23 of the Revised Code may obtain a court order under this division for the disinterment of the remains of the decedent.
Source ORC 517 2927.11 4767 1721 cemeteries · page 6 · version 2023-08-01
In force from 2023-04-03 to 2026-10-03, section 517.24
517.24: version effective 2023-04-03, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 18
No person, without privilege to do so, shall purposely deface, damage, pollute, or otherwise physically mistreat any of the following: (1) The flag of the United States or of this state; (2) Any public monument; (3) Any historical or commemorative marker, or any structure, Indian mound or earthwork, cemetery, thing, or site of great historical or archaeological interest;
Source ORC 517 2927.11 4767 1721 cemeteries · page 18 · version 2023-08-01
In force from 1999-09-20 to 2026-10-03, section 2927.11
2927.11: version effective 1999-09-20, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 22
(D) Sections 4767.02 to 4767.04 of the Revised Code do not apply to or affect a family cemetery or a cemetery in which there have been no interments during the previous twenty-five calendar years.
Source ORC 517 2927.11 4767 1721 cemeteries · page 22 · version 2023-08-01
In force from 2018-10-29 to 2026-10-03, section 4767.02
4767.02: version effective 2018-10-29, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 6
Regardless of whether or not a cemetery, burial mound, or other burial place is found eligible for listing in the NRHP, SHPO recommends preservation-in-place as the preferred treatment. The only exception is for cases where all parties, including lineal descendants and/or culturally affiliated groups or individuals, agree that removal/disinterment is the best option.
Source OHC SHPO archaeology guidelines section cemeteries burial mounds · page 6 · version 2022-11
May be cited on the cut-off date.
Quoted from the law, page 10
The buffer must be depicted on project construction plans and delineated by temporary fencing prior to and during construction. If a 100-foot buffer is not possible, geophysical investigations must be used to try and delineate the horizontal extent of the interments followed by consultation with the SHPO to determine the extent of the avoidance area
Source OHC SHPO archaeology guidelines section cemeteries burial mounds · page 10 · version 2022-11
May be cited on the cut-off date.
Quoted from the law, page 11
encountered during any phase of compliance-related activities and/or construction activities, all ground disturbing activities within a 150-foot radius of the burial place must cease and the human remains, burial facility and associated funerary objects must be covered and secured. The discovery must be reported to the county medical examiner/coroner, local law enforcement, the agency/applicant, landowner, and the SHPO.
Source OHC SHPO archaeology guidelines section cemeteries burial mounds · page 11 · version 2022-11
May be cited on the cut-off date.
4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
Medium priority (1)
IR-1be216979f · Medium priority
Provide the shpo / thpo correspondence for the project area, or confirm none exists.
	Missing evidence
	SHPO / THPO correspondence

	Consequence
	Archaeological Resources and Cemeteries is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Shift array layout to avoid 33-CR-0412 with buffer, or complete Phase II testing.
Conduct ground-penetrating radar at the cemetery; fence buffer during construction.
Submit survey to SHPO and adopt unanticipated discovery plan; begin tribal outreach.
Agencies
OPSB
OHPO
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-01.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (4)
Cultural Resources Literature Review and Phase I Archaeological Survey - Tamsin Ridge · DR-0008 · 2023-06-30 · pages 1, 2, 3
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · 2023-03-28 · page 1
Glare, Aviation and Visual Memo - Tamsin Ridge Solar and Storage Project · DR-0015 · 2023-04-25 · page 2
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · 2023-04-18 · page 3
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-01

	Engine version
	2.11.0

	Prompt version
	2026-11-08.1

	Rows pack
	rows.json sha256 a018ecd7e4703bc1

	Federal pack
	federal.json sha256 8841c555ff35d20b

	State pack
	oh.json sha256 d4780705e1f18d09

	Local pack
	oh_carroll_county.json sha256 905cd3308848e7e8

	Data room manifest
	0c7e80d0ad17d1e3ed4060b9702e5b1905060ae2896e9aad796a57b590005832

	Audit chain
	valid (19 events)

	QA status
	PASS_WITH_WARNINGS

	Rendered at
	2026-11-10T15:42:40+00:00

	Run record (annex)
	66fca2c4c0bfa90df1e8efb79c0d2f426536b41f50a6a9b6869dd85e4554fd50

	Legal source index
	6974703924a38a8e90717222e31e444b8e540aca9b6cec809ad4ddc5b0691ca9

	Exporter
	Prism/room/exporter 1.4.0
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