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Land Use and Site Features: desk report
Tamsin Ridge Solar and Storage
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, EN-01 Land Use and Site Features, in the Environmental Resources section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-01

	Row in the matrix
	EN-01 Land Use and Site Features


1 Finding
3  Resource is present, likely difficult to address
The engine shows this rating as 3
	The rule
	Code computed the rating from the assessor's inputs:
extent=core, avoidable=partly -> 3
Set by the rule

	Decision
	Released with flags

	The engine's reasons
	Independent assessments split on the category (7 samples: {'2': 2, '3': 4, '1': 1}); reviewer to confirm

	Evidence state
	VERIFIED · field study or agency determination


The assessor's comments
Existing 138 kV line crosses the West Block. Gas gathering pipeline crosses Parcels 5, 7 and 10; Parcel 5 also carries an oil and gas lease. Two plugged wells and abandoned mine workings are present. Lessee's planned second pad overlaps about 9 acres of the array layout.
Worst case
The same rule on the worst case gives no rating above the point.
	Scenario
	The lessee's second pad and pipeline easement rights, with right to add lines, conflict with the array and substation/BESS yard on Parcels 2 and 5, requiring uncertain easement releases or relocation.

	Step still pending
	Site constraints mapping and negotiations with Brenwick Exploration and Calder Gathering

	Inputs in the worst case
	Extent core · Avoidable no · Pathway individual · Impact likely yes

	The rule on the worst case
	worst case (extent=core, avoidable=no -> 3) not above the point

	Claims that make it plausible
	C-7d33945087, C-dcf3900993, C-f23ef8892f, C-df8aadf77e


2 What the record shows
The five inputs
Present: yes
Documents describe constraining features: 138 kV line across the West Block (C-ad2c42da82), gathering pipeline across Parcels 5, 7 and 10 (C-bf7087e782), plugged wells and abandoned mine (C-a3cebd779c, C-d9db0a1832). The farming/no-industrial-use statement (C-e9a687c1a0) concerns historic industrial use and does not negate these features.
Cites C-ad2c42da82, C-bf7087e782, C-a3cebd779c, C-d9db0a1832, C-e9a687c1a0
Extent: core
The 138 kV line crosses the West Block (C-ad2c42da82); the gathering pipeline, 50-foot easement, transmission ROW and oil and gas lease encumber Parcel 5, which hosts the substation and BESS yard (C-df8aadf77e, C-f23ef8892f, C-c22072d6dc, C-dcf3900993); the abandoned mine lies beneath the eastern part (C-d9db0a1832). Features cross the site and key facilities.
Cites C-ad2c42da82, C-df8aadf77e, C-f23ef8892f, C-c22072d6dc, C-dcf3900993, C-d9db0a1832
Avoidable: partly
Setbacks (100 feet from plugged wells, operator setbacks) allow siting around most features (C-28570f896a, C-af471048ff). However, the lessee's planned second pad overlaps about 9 acres of the array layout (C-7d33945087), the lessee holds surface-use rights (C-dcf3900993), and the substation sits on an encumbered parcel (C-df8aadf77e); no layout or constraints map is in the data room, so full avoidance is not shown.
Cites C-28570f896a, C-af471048ff, C-7d33945087, C-dcf3900993, C-df8aadf77e
Pathway: standard
Crossing agreements with Calder Gathering (C-d257ecfe8e), operator and ODNR setbacks, and coordination with the oil and gas lessee are standard consents and setbacks; no documented relocation with uncertain outcome.
Cites C-d257ecfe8e, C-af471048ff, C-28570f896a
Impact likely: yes
Pipeline, ROW, well setbacks and the lessee pad overlap (about 9 acres) remove buildable area and constrain layout, including on the substation/BESS parcel (C-7d33945087, C-28570f896a, C-f23ef8892f, C-df8aadf77e).
Cites C-7d33945087, C-28570f896a, C-f23ef8892f, C-df8aadf77e
Supporting statements (13)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-28570f896a
Structures should be kept at least 100 feet from plugged wells and follow the operator's setbacks from the pad and flowlines.
Quoted from page 1
Keep structures at least 100 feet from plugged wells, and follow
 the operator's setbacks from the pad and its flowlines.
Preliminary Geotechnical Engineering Report - Tamsin Ridge Solar and Storage Project · DR-0018 · Page 1 · 2023-05-15
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Cited by EN-02 · Filed under EN-01, EN-02
C-7d33945087
The lessee's planned second pad on Parcel 2 overlaps about 9 acres of the array layout.
Quoted from page 2
The lessee's planned second pad on Parcel 2 overlaps about 9 acres of the
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · Page 2 · 2023-05-30
Source developer_document · Claim type presence · Polarity presence · Confidence low · Quote check exact, 100 of 100
Cited by PE-05 · Filed under EN-01, EN-02, PE-05
C-a3cebd779c
Two plugged and abandoned oil and gas wells are within the project area, and an active horizontal Utica well pad adjoins it.
Quoted from page 1
two
 plugged and abandoned oil and gas wells within the project area and an active horizontal Utica well pad adjoining it.
ODNR Environmental Review - Tamsin Ridge Solar and Storage Project (ODNR 23-0477) · DR-0011 · Page 1 · 2023-05-02
Source agency_determination · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-02 · Filed under EN-01, EN-02
C-ad2c42da82
An existing 138 kV transmission line crosses the West Block.
Quoted from page 1
An existing 138 kV transmission line crosses the West Block
Tamsin Ridge Solar and Storage Project - Project Description · DR-0001 · Page 1 · 2023-06-12
Source developer_document · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-af471048ff
Plugged wells should be surveyed and fenced, keeping setbacks required by the operator and ODNR.
Quoted from page 1
Survey and fence the plugged wells and keep the setbacks the operator and ODNR require.
Phase I Environmental Site Assessment - Tamsin Ridge Solar and Storage Project · DR-0012 · Page 1 · 2023-01-27
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Filed under EN-01, EN-02
C-bf7087e782
A natural gas gathering pipeline crosses Parcels 5, 7 and 10.
Quoted from page 1
a natural gas gathering pipeline across Parcels 5, 7 and 10
Phase I Environmental Site Assessment - Tamsin Ridge Solar and Storage Project · DR-0012 · Page 1 · 2023-01-27
Source consultant_memo · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EN-01, PE-05
C-c22072d6dc
A 100-foot transmission line right-of-way with tree clearing rights affects Parcel 5.
Quoted from page 2
a 100-foot right-of-way for a transmission line, with tree clearing rights.
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 2 · 2023-04-18
Source public_record · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EN-01, PE-05
C-d257ecfe8e
The easement crosses the Calder Gathering Company natural gas gathering line, requiring the grantee to obtain a written crossing agreement and keep required clearance.
Quoted from page 1
Grantee will obtain that company's written crossing agreement and keep the clearance it requires.
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · Page 1 · 2022-11-03
Source public_record · Claim type constraint · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by PE-03, PE-05 · Filed under EN-01, PE-03, PE-05
C-d9db0a1832
Records show abandoned underground Elsby No. 2 Mine beneath the eastern part of the project area, plus pre-1977 reclaimed surface mining.
Quoted from page 1
Division records show abandoned underground coal mining, the Elsby No. 2 Mine in the Upper Freeport (No. 7)
 coal, beneath the eastern part of the project area
ODNR Environmental Review - Tamsin Ridge Solar and Storage Project (ODNR 23-0477) · DR-0011 · Page 1 · 2023-05-02
Source agency_determination · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-02 · Filed under EN-01, EN-02
C-dcf3900993
An oil and gas lease to Brenwick Exploration, with pooled unit, allows surface use for wells, pads, roads, pipelines and tanks on Parcels 2 and 5.
Quoted from page 2
surface as is reasonably necessary for wells, pads, roads, pipelines and tanks. Affects Parcels 2 and 5.
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 2 · 2023-04-18
Source public_record · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by PE-05 · Filed under EN-01, EN-02, PE-05
C-df8aadf77e
Parcel 5 hosts the substation and BESS yard and has a 138 kV line, gathering pipeline and oil and gas lease.
Quoted from page 1
Substation, BESS yard; 138 kV line; gathering pipeline; oil and gas lease
Parcel Schedule 2023-07-14 · DR-0005 · Page 1 · 2023-07-14
Source developer_document · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Cited by EN-04 · Filed under EN-01, PE-05
C-e9a687c1a0
Aerial photos and records show farming since at least 1939 and no industrial use found.
Quoted from page 2
No industrial use was found.
Phase I Environmental Site Assessment - Tamsin Ridge Solar and Storage Project · DR-0012 · Page 2 · 2023-01-27
Source desktop_study · Claim type absence · Polarity absence · Confidence high · Quote check exact, 100 of 100
Filed under EN-01, EN-04
C-f23ef8892f
A 50-foot permanent gas gathering pipeline easement to Calder Gathering, with right to add lines, affects Parcel 5.
Quoted from page 2
a 50-foot permanent easement for natural gas gathering lines, with the right to
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 2 · 2023-04-18
Source public_record · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EN-01, PE-05
3 Permits and requirements
The requirements tied to the rows of this report, by level. Each quote from dated law is shown with its source, the version in force on the cut-off and the basis for it.
No requirement is tied to the rows of this report.
4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
High priority (1)
IR-e8a82effe6 · High priority
Provide the site layout or constraints map for the project area, or confirm none exists.
	Missing evidence
	Site layout or constraints map

	Consequence
	Land Use and Site Features is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Prepare site constraints map from title and ODNR data.
Negotiate crossing agreements and surface-use accommodation with Calder Gathering and Brenwick.
Site layout to apply well and pipeline setbacks.
Agencies
ODNR
Carroll County
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-01.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (8)
Preliminary Geotechnical Engineering Report - Tamsin Ridge Solar and Storage Project · DR-0018 · 2023-05-15 · page 1
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · 2023-05-30 · page 2
ODNR Environmental Review - Tamsin Ridge Solar and Storage Project (ODNR 23-0477) · DR-0011 · 2023-05-02 · page 1
Tamsin Ridge Solar and Storage Project - Project Description · DR-0001 · 2023-06-12 · page 1
Phase I Environmental Site Assessment - Tamsin Ridge Solar and Storage Project · DR-0012 · 2023-01-27 · pages 1, 2
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · 2023-04-18 · page 2
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · 2022-11-03 · page 1
Parcel Schedule 2023-07-14 · DR-0005 · 2023-07-14 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-01

	Engine version
	2.11.0

	Prompt version
	2026-11-08.1

	Rows pack
	rows.json sha256 a018ecd7e4703bc1

	Federal pack
	federal.json sha256 8841c555ff35d20b

	State pack
	oh.json sha256 d4780705e1f18d09

	Local pack
	oh_carroll_county.json sha256 905cd3308848e7e8

	Data room manifest
	0c7e80d0ad17d1e3ed4060b9702e5b1905060ae2896e9aad796a57b590005832

	Audit chain
	valid (19 events)

	QA status
	PASS_WITH_WARNINGS

	Rendered at
	2026-11-10T15:42:40+00:00

	Run record (annex)
	66fca2c4c0bfa90df1e8efb79c0d2f426536b41f50a6a9b6869dd85e4554fd50

	Exporter
	Prism/room/exporter 1.4.0
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