
Tamsin Ridge Solar and Storage · Agricultural Resources: desk report
Agricultural Resources: desk report
Tamsin Ridge Solar and Storage
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, EN-03 Agricultural Resources, in the Environmental Resources section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-01

	Row in the matrix
	EN-03 Agricultural Resources


1 Finding
3  Resource is present, likely difficult to address
The engine shows this rating as 3
	The rule
	Code computed the rating from the assessor's inputs:
extent=core, avoidable=partly -> 3
Set by the rule

	Decision
	Released

	Evidence state
	REPORTED · desktop, consultant or developer record


The assessor's comments
SSURGO maps about 62 percent of the land as prime farmland. Twelve parcels are enrolled in CAUV and eight are in an agricultural district; recoupment may apply unless the energy facility exception applies. Field tile is reported in West Block fields. Harrison Township No. 4 county ditch crosses Parcel 3, with a 25-foot maintenance easement.
Worst case
The same rule on the worst case gives no rating above the point.
	Scenario
	Extensive untiled-map tile damage, full CAUV recoupment and district withdrawal penalties, and a ditch improvement petition for a crossing; still manageable through standard processes.

	Step still pending
	Drain tile locating survey, county auditor confirmation of the energy facility exception, and county engineer review of ditch crossings

	Inputs in the worst case
	Extent core · Avoidable partly · Pathway standard · Impact likely yes

	The rule on the worst case
	worst case (extent=core, avoidable=partly -> 3) not above the point

	Claims that make it plausible
	C-c8e5735fc6, C-1a003c9f9c, C-d07aa54486, C-b49803fd5c


2 What the record shows
The five inputs
Present: yes
Prime farmland (C-dd848d6716), CAUV and agricultural district enrollment (C-1a003c9f9c, C-bead1c4d82), field tile (C-682e211cfb, C-c8e5735fc6) and the Harrison Township No. 4 county ditch (C-d07aa54486) are documented.
Cites C-dd848d6716, C-1a003c9f9c, C-bead1c4d82, C-682e211cfb, C-c8e5735fc6, C-d07aa54486
Extent: core
SSURGO maps about 62 percent prime farmland plus 21 percent statewide importance (C-dd848d6716). Twelve parcels are in CAUV and eight in an agricultural district (C-1a003c9f9c). Landowners report tile across most West Block parcels (C-c8e5735fc6), and the ditch crosses Parcel 3 (C-d07aa54486). Program enrollment affects much of the site.
Cites C-dd848d6716, C-1a003c9f9c, C-c8e5735fc6, C-d07aa54486
Avoidable: partly
Costs are tile repair or rerouting (C-50cd3eb7bc, C-f3753971f3, C-b49803fd5c) and CAUV recoupment and withdrawal penalty, unless the energy facility exception applies (C-1a003c9f9c, C-78fa553551). No binding agricultural easement is documented, so not 'no'.
Cites C-50cd3eb7bc, C-f3753971f3, C-b49803fd5c, C-1a003c9f9c, C-78fa553551
Pathway: standard
Recoupment is a charge, not a permit (OH-AG). OPSB requires mapping of agricultural district land and a tile repair plan (C-752c6c08a4). A county ditch petition is needed only if the ditch is altered (OH-DITCH, C-83e349f335). No discretionary easement approval or prohibition is documented. No federal nexus is shown for the FPPA.
Cites C-752c6c08a4, C-83e349f335
Impact likely: yes
Tile damage during grading, trenching and collection lines is likely on tiled West Block fields (C-682e211cfb, C-c8e5735fc6). Farmland conversion and possible recoupment are also likely (C-78fa553551, C-67ba142a5a).
Cites C-682e211cfb, C-c8e5735fc6, C-78fa553551, C-67ba142a5a
Supporting statements (13)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-1a003c9f9c
Twelve parcels are enrolled in CAUV and eight are in an agricultural district; recoupment charge and withdrawal penalty may apply unless the energy facility exception applies.
Quoted from page 3
Twelve parcels are enrolled in
CAUV and eight are in an agricultural district
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source consultant_memo · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-50cd3eb7bc
Grantee must repair or reroute any drain tile it damages within thirty days.
Quoted from page 1
repair or reroute any drain tile it damages within thirty (30) days
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · Page 1 · 2022-11-03
Source public_record · Claim type constraint · Polarity presence · Confidence medium · Quote check exact, 100 of 100
C-67ba142a5a
Cropland covers about 818 acres (72%) of the Project Area, mostly on prime farmland soils.
Quoted from page 2
Cropland (corn, soybeans)                818           72%                    Mostly prime farmland soils
Bat Habitat Assessment and Vegetation Survey - Tamsin Ridge Solar and Storage Project · DR-0007 · Page 2 · 2023-06-20
Source field_study · Claim type extent · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Cited by EC-03 · Filed under EC-03, EN-03
C-682e211cfb
Field tile was seen in 2 test pits on the West Block slopes.
Quoted from page 2
Field tile seen in 2 test pits
Preliminary Geotechnical Engineering Report - Tamsin Ridge Solar and Storage Project · DR-0018 · Page 2 · 2023-05-15
Source field_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EG-02, EN-03
C-752c6c08a4
Staff expects mapping of agricultural district land and a drain tile repair plan.
Quoted from page 1
Mapping of agricultural district land and a drain tile repair plan.
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · Page 1 · 2023-03-28
Source agency_determination · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-78fa553551
A CAUV recoupment charge becomes due when land is converted from agricultural use.
Quoted from page 1
including any CAUV recoupment charge that becomes due when land is
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 1 · 2023-04-18
Source public_record · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EN-03, PE-06
C-83e349f335
County ditch has a maintenance easement within 25 feet of the top of each bank; fencing, piles and equipment are kept out.
Quoted from page 3
with a maintenance easement within
25 feet of the top of each bank.
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source consultant_memo · Claim type constraint · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EN-03, PE-05
C-b49803fd5c
A drain tile locating survey should be done before final design, and tile cut by project work must be repaired or rerouted.
Quoted from page 3
A drain tile locating survey (aerial imagery, probing and test pits) should be done
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
C-bead1c4d82
Parcels 2, 5 and 9 are enrolled in the CAUV program and subject to recoupment on conversion to non-agricultural use.
Quoted from page 2
enrolled in the current agricultural use value (CAUV) program and are subject to recoupment on conversion to a
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · Page 2 · 2023-04-18
Source public_record · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-c8e5735fc6
Landowners report subsurface drain tile in the West Block fields on Parcels 1 to 4, 6 and 8 and Parcel 14; no tile maps exist.
Quoted from page 3
Landowners report subsurface drain tile in the West Block fields on Parcels 1 to 4, 6 and 8 and on
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source consultant_memo · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under EG-02, EN-03
C-d07aa54486
Harrison Township No. 4 county ditch crosses Parcel 3 and runs along the southern line of Parcel 5, with a maintenance easement within 25 feet of each bank top.
Quoted from page 3
The Harrison Township No. 4 county ditch crosses Parcel 3 and runs along the southern line of
Parcel 5.
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source consultant_memo · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under AQ-01, EN-01, EN-03, PE-05
C-dd848d6716
SSURGO maps about 62 percent of the land as prime farmland and another 21 percent as farmland of statewide importance.
Quoted from page 3
maps about 62 percent of the land as prime farmland and another 21 percent
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · Page 3 · 2023-06-05
Source desktop_study · Claim type presence · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-f3753971f3
Standard lease provides that lessee repairs or reroutes drain tile damaged by construction.
Quoted from page 1
Lessee repairs or reroutes tile damaged by construction
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · Page 1 · 2023-05-30
Source developer_document · Claim type presence · Polarity presence · Confidence medium · Quote check exact, 100 of 100
3 Permits and requirements
The requirements tied to the rows of this report, by level. Each quote from dated law is shown with its source, the version in force on the cut-off and the basis for it.
Federal (1)
Farmland conversion impact rating (Form AD-1006)
F-FPPA · USDA Natural Resources Conservation Service
	Applicability
	Conditional

	Instrument
	Farmland Protection Policy Act (7 U.S.C. 4201 et seq.); 7 CFR Part 658

	Trigger
	Federal funding or assistance for a project that converts prime, unique or important farmland. Federal permits for activities on private land are not a federal program under 7 CFR 658.2.

	Description
	Applies to projects with federal funding or assistance that convert important farmland.

	Typical timeline
	NRCS responds to a request within 10 working days of receipt, or in 30 working days where a site visit or land evaluation system design is needed (7 CFR 658.4(a)).

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:federal

	In the permit matrix
	F-FPPA


Legal basis: 4 quotes from dated law
Quoted from the law, page 1
Federal program means those activities or responsibilities of a Federal agency that involve undertaking, financing, or assisting construction or improvement projects or acquiring, managing, or disposing of Federal lands and facilities. (1) The term “Federal program” does not include: (i) Federal permitting, licensing, or rate approval programs for activities on private or non-Federal lands
Source 7CFR658 · page 1 · version 2023-08-01
Cited for requirement and trigger (federal program; permits excluded)
In force from 2016-11-23 to 2026-10-07
eCFR versioner: 7 CFR part 658, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-11-23
May be cited on the cut-off date.
Quoted from the law, page 1
Farmland means prime or unique farmlands as defined in section 1540(c)(1) of the Act or farmland that is determined by the appropriate state or unit of local government agency or agencies with concurrence of the Secretary to be farmland of statewide of local importance.
Source 7CFR658 · page 1 · version 2023-08-01
Cited for trigger: farmland
In force from 2016-11-23 to 2026-10-07
eCFR versioner: 7 CFR part 658, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-11-23
May be cited on the cut-off date.
Quoted from the law, page 1
NRCS will respond to these requests within 10 working days of their receipt except that in cases where a site visit or land evaluation system design is needed, NRCS will respond in 30 working days.
Source 7CFR658 · page 1 · version 2023-08-01
Cited for timeline: NRCS response to Form AD-1006 request
In force from 2016-11-23 to 2026-10-07
eCFR versioner: 7 CFR part 658, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-11-23
May be cited on the cut-off date.
Quoted from the law, page 1
The term “Federal program” does not include: (i) Federal permitting, licensing, or rate approval programs for activities on private or non-Federal lands
Source 7CFR658 · page 1 · version 2023-08-01
In force from 2016-11-23 to 2026-10-07
eCFR versioner: 7 CFR part 658, same text on 2021-10-15, 2022-05-20, 2022-09-12, 2023-04-22, 2023-08-01 and on every amendment date between them; amendment dates 2016-11-23
May be cited on the cut-off date.
State (2)
Recoupment of CAUV tax savings and agricultural district withdrawal penalty when land leaves agricultural use, and the OPSB's review of agricultural district land (a cost and a review, not a permit)
OH-AG · County auditor (agricultural district and CAUV administration, recoupment charge, withdrawal penalty); Ohio Power Siting Board (OPSB) (agricultural district impact in the certificate decision)
	Applicability
	Conditional

	Instrument
	ORC 929.01 to 929.05 (agricultural districts); ORC 5713.30 to 5713.38 (current agricultural use valuation, CAUV); ORC 4906.10(A)(7); OAC 4906-4-08(E)

	Trigger
	Land enrolled in CAUV or an agricultural district is converted to a non-agricultural use by the project.

	Description
	Two county programs govern farmland: current agricultural use value (CAUV), a property-tax relief program, and agricultural districts under ORC Chapter 929. Neither is a permit; the cost arises when land leaves agricultural use. On conversion, a charge is levied equal to the tax savings on the converted land over the three preceding tax years. Withdrawal from an agricultural district, which includes conversion to a non-agricultural use, adds a penalty of a percentage of that charge equal to the average bank prime rate. No charge is levied where the conversion is incident to constructing an energy facility, as defined in ORC 5727.01, and the rest of the parcel stays in agricultural use; that definition was not in the source library, so confirm that a solar and storage facility qualifies. The OPSB weighs impact on agricultural district land in its certificate findings and requires agricultural and district land to be mapped.

	Typical timeline
	The CAUV recoupment reaches back three tax years before the year of conversion (ORC 5713.34(A)(1)); the district penalty uses the average bank prime rate at the time that charge is required to be paid (ORC 929.02(D)(1)(a)).

	Version of the law on the cut-off
	As in force from 2023-01-28 (the library text)

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:oh.json

	In the permit matrix
	OH-AG


Legal basis: 8 quotes from dated law
Quoted from the law, page 1
A companion law is the current agricultural use valuation (CAUV) program. The CAUV provides relief on farmland property taxes. Please contact your local county auditor's office for more information about the agricultural district or CAUV programs.
Source ODA agricultural district form page · page 1 · version 2023-01-28
May be cited on the cut-off date.
Quoted from the law, page 1
"Withdrawal from an agricultural district" includes the explicit removal of land from an agricultural district, conversion of land in an agricultural district to use for purposes other than agricultural production, and withdrawal of land from a land retirement or conservation program to use for purposes other than agricultural production.
Source ORC 929 5713 5301 farmland CAUV easements · page 1 · version 2023-08-01
In force from 2020-03-27 to 2026-10-03, section 929.01
929.01: version effective 2020-03-27, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 5
the owner shall pay a percentage of the amount charged under section 5713.34 of the Revised Code that is equal to the average bank prime rate at the time the amount charged under that section is required to be paid. The withdrawal penalty shall be in addition to the amount charged under that section.
Source ORC 929 5713 5301 farmland CAUV easements · page 5 · version 2023-08-01
In force from 2018-11-02 to 2026-10-03, section 929.02
929.02: version effective 2018-11-02, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 29
a portion of the tax savings upon such converted land shall be recouped as provided for by Section 36, Article II, Ohio Constitution by levying a charge on such land in an amount equal to the amount of the tax savings on the converted land during the three tax years immediately preceding the year in which the conversion occurs.
Source ORC 929 5713 5301 farmland CAUV easements · page 29 · version 2023-08-01
In force from 2017-09-29 to 2025-04-02, section 5713.34
5713.34: version effective 2017-09-29; first change after it 2025-04-03 (H.B. 315, 135th GA), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 29
A charge shall not be levied under this section for the conversion of a portion of a tract, lot, or parcel of land devoted exclusively to agricultural use if the conversion is incident to the construction or installation of an energy facility, as defined in section 5727.01 of the Revised Code
Source ORC 929 5713 5301 farmland CAUV easements · page 29 · version 2023-08-01
In force from 2017-09-29 to 2025-04-02, section 5713.34
5713.34: version effective 2017-09-29; first change after it 2025-04-03 (H.B. 315, 135th GA), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 21
shall not cause the remaining portion of the tract, lot, or parcel to be regarded as a conversion of land devoted exclusively to agricultural use if the remaining portion of the tract, lot, or parcel continues to be devoted exclusively to agricultural use.
Source ORC 929 5713 5301 farmland CAUV easements · page 21 · version 2023-08-01
In force from 2021-04-12 to 2025-04-02, section 5713.30
5713.30: version effective 2021-04-12; first change after it 2025-04-03 (H.B. 315, 135th GA), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 17
what its impact will be on the viability as agricultural land of any land in an existing agricultural district established under Chapter 929. of the Revised Code that is located within the site and alternative site of the proposed major utility facility.
Source ORC 4906 Power Siting Board · page 17 · version 2023-08-01
In force from 2021-10-11 to 2025-08-13, section 4906.10
4906.10: version effective 2021-10-11; first change after it 2025-08-14 (Am. Sub. H.B. 15, 136th GA), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Quoted from the law, page 31
The applicant shall provide information regarding agricultural districts and potential impacts to agricultural land. (1) Mapping of agricultural land. The applicant shall identify on a map of at least 1:24,000 scale the proposed facility, all agricultural land, and separately all agricultural district land existing at least sixty days prior to submission of the application located within the project area boundaries.
Source OAC 4906 4 OPSB generation facility applications · page 31 · version 2023-08-01
In force from 2018-04-26 to 2024-05-29, section 4906-4-08
4906-4-08: version effective 2018-04-26; first change after it 2024-05-30 (OPSB Case 21-902-GE-BRO (determination 2023-07-20)), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
Petition proceeding before the board of county commissioners (or joint board) for any alteration of a county or joint county ditch, respect for the county's maintenance easement, and field tile protection and repair under the OPSB rules
OH-DITCH · Board of county commissioners (or the joint board of county commissioners for a joint county ditch) and the county engineer; Ohio Power Siting Board (OPSB) (field tile requirements in the certificate application)
	Applicability
	Conditional

	Instrument
	ORC Chapters 6131, 6133 and 6137 (versions effective 2021-03-24); OAC 4906-4-08(E)

	Trigger
	The project would alter a county or joint county ditch, or build in the strip along it that maintenance crews may use.

	Description
	A petition for a county ditch goes to the board of county commissioners; where land in two or more counties is affected, a joint board of the counties' commissioners conducts the proceeding. For a single county ditch the county engineer has general charge of repair and maintenance. Filling, tiling, boxing, arching, relocating or otherwise changing a ditch is an improvement, which begins with a petition to the board. The permanent maintenance easement is not more than twenty-five feet from the top of the bank on an open ditch and not more than eighty feet centered on the centerline of a closed ditch. The chapters do not themselves set out a separate ditch-crossing permit, so confirm with the county engineer what a crossing needs. The OPSB application must show avoidance or minimization of damage to field tile and timely repair at the applicant's expense.

	Typical timeline
	After a petition is filed, the board sets a view between thirty and one hundred twenty days later and a first hearing thirty to ninety days after the view (ORC 6131.07(B)).

	Verification
	PACK_PENDING_QUALIFIED_REVIEW

	Source
	pack:oh.json

	In the permit matrix
	OH-DITCH


Legal basis: 8 quotes from dated law
Quoted from the law, page 1
"Improvement" includes: (1) The location, construction, reconstruction, reconditioning, widening, deepening, straightening, altering, boxing, tiling, filling, walling, arching, or any change in the course, location, or terminus of any ditch, drain, watercourse, or floodway;
Source ORC 6131 6133 6137 county ditches · page 1 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6131.01
6131.01: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 6
Any owner may file a petition for the construction of a drainage improvement with the clerk of the board of county commissioners of the county in which is located a part of the land proposed to benefit from the improvement.
Source ORC 6131 6133 6137 county ditches · page 6 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6131.04
6131.04: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 10
which shall be between thirty and one hundred twenty days after the date on which the petition was filed with the clerk; (2) Establish a date and hour between thirty and ninety days after the date set for the view, when it will hold its first hearing on the petition.
Source ORC 6131 6133 6137 county ditches · page 10 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6131.07
6131.07: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 79
When an improvement is proposed to be located in or benefits or damages land in two or more counties, the proceeding shall be conducted by a joint board of county commissioners consisting of the members of the boards of county commissioners of the several counties in which land may be benefited or damaged by the proposed improvement.
Source ORC 6131 6133 6137 county ditches · page 79 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6133.02
6133.02: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 101
With regard to a single county improvement, the county engineer has general charge and supervision of the repair and maintenance of all county drainage improvements constructed under Chapters 940., 6131., 6133., and 6135. of the Revised Code.
Source ORC 6131 6133 6137 county ditches · page 101 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6137.06
6137.06: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 111
In the case of open ditches, the permanent easement so used shall be not more than twenty-
five feet from the top of the bank, measured at right angles thereto, and wherever practical the area so used shall be on one side of the ditch only.
Source ORC 6131 6133 6137 county ditches · page 111 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6137.12
6137.12: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 111
The maximum width of permanent easement for closed ditches shall not exceed eighty feet centered on the centerline of the improvement.
Source ORC 6131 6133 6137 county ditches · page 111 · version 2023-08-01
In force from 2021-03-24 to 2026-10-03, section 6137.12
6137.12: version effective 2021-03-24, still the current version when the page map was checked (2026-10-03)
May be cited on the cut-off date.
Quoted from the law, page 32
Avoidance or minimization to the maximum extent practicable of any damage to field tile drainage systems and soils in agricultural areas. (ii) Timely repair of damaged field tile systems to at least original conditions, at the applicant's expense.
Source OAC 4906 4 OPSB generation facility applications · page 32 · version 2023-08-01
In force from 2018-04-26 to 2024-05-29, section 4906-4-08
4906-4-08: version effective 2018-04-26; first change after it 2024-05-30 (OPSB Case 21-902-GE-BRO (determination 2023-07-20)), from codes.ohio.gov version history in archive captures (confirmed_two_sources)
May be cited on the cut-off date.
4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
High priority (1)
IR-847cfb1cc8 · High priority
Provide the soil survey or farmland classification review for the project area, or confirm none exists.
	Missing evidence
	Soil survey or farmland classification review

	Consequence
	Agricultural Resources is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Complete drain tile locating survey and prepare tile repair plan before final design.
Confirm with county auditor and counsel whether the energy facility exception covers recoupment.
Map agricultural district land for OPSB; keep equipment out of ditch easement.
Agencies
OPSB
Carroll County Auditor
Carroll County Engineer
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-01.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (7)
Stormwater, Floodplain and Drainage Memo - Tamsin Ridge Solar and Storage Project · DR-0019 · 2023-06-05 · page 3
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · 2022-11-03 · page 1
Bat Habitat Assessment and Vegetation Survey - Tamsin Ridge Solar and Storage Project · DR-0007 · 2023-06-20 · page 2
Preliminary Geotechnical Engineering Report - Tamsin Ridge Solar and Storage Project · DR-0018 · 2023-05-15 · page 2
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · 2023-03-28 · page 1
Commitment for Title Insurance No. ATA-23-0418 (Parcels 2, 5 and 9) · DR-0006 · 2023-04-18 · pages 1, 2
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · 2023-05-30 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-01

	Engine version
	2.11.0

	Prompt version
	2026-11-08.1

	Rows pack
	rows.json sha256 a018ecd7e4703bc1

	Federal pack
	federal.json sha256 8841c555ff35d20b

	State pack
	oh.json sha256 d4780705e1f18d09
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	Data room manifest
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