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Decommissioning and Financial Assurance: desk report
Tamsin Ridge Solar and Storage
This is a fictional demonstration project in which every organisation, person, parcel and finding is invented.
One row of the risk matrix, PE-06 Decommissioning and Financial Assurance, in the Additional Permitting section: what the record holds on it.
A desk review of the record as it stood: not a field survey and not a modelled study.
	Information cut-off
	2023-08-01

	Row in the matrix
	PE-06 Decommissioning and Financial Assurance


1 Finding
3  Resource is present, likely difficult to address
The engine shows this rating as 3
	The rule
	Code computed the rating from the assessor's inputs:
extent=core, avoidable=partly -> 3
Set by the rule

	Decision
	Released

	Evidence state
	REPORTED · desktop, consultant or developer record


The assessor's comments
ORC 4906.21 to 4906.222 require a decommissioning plan and performance bond. Bond equal to the estimate is due before construction, updated every five years, never reduced. Estimate is $11.6 million gross, $5.7 million net of salvage; OPSB treatment of salvage is unsettled. Leases require 36-inch removal and separate landowner security.
Worst case
The same rule on the worst case gives no rating above the point.
	Scenario
	OPSB requires the gross $11.6 million bond with no salvage credit, and the amount is contested through the OPSB process, with landowner security adding further burden.

	Step still pending
	OPSB review of the decommissioning plan and bond amount

	Inputs in the worst case
	Extent core · Avoidable partly · Pathway individual · Impact likely yes

	The rule on the worst case
	worst case (extent=core, avoidable=partly -> 3) not above the point

	Claims that make it plausible
	C-7f2ea3298c, C-303a605026, C-b508b5b110, C-0dda429c60


2 What the record shows
The five inputs
Present: yes
OPSB pre-application summary confirms ORC 4906.21 to 4906.222 decommissioning plan and performance bond requirements apply (C-7818388af6). Lease requires removal to 36 inches and soil restoration (C-00d4067593), with separate security per landowner (C-f3daa0fd5a).
Cites C-7818388af6, C-00d4067593, C-f3daa0fd5a
Extent: core
State statute and the bond govern the whole project; leases require removal and restoration across leased land (C-7818388af6, C-0dda429c60, C-e278af1a95). The Parcel 7 collection easement adds removal of above-ground equipment two years after operations stop (C-4e2febbe42).
Cites C-7818388af6, C-0dda429c60, C-e278af1a95, C-4e2febbe42
Avoidable: partly
Terms are front-loaded: a bond equal to the estimate must be posted before construction, updated every five years and never reduced (C-0dda429c60). Whether OPSB accepts the net-of-salvage figure ($5.7M) or requires gross ($11.6M) is unsettled, and salvage values are volatile (C-303a605026, C-7f2ea3298c, C-b508b5b110). Leases also require separate security per landowner (C-f3daa0fd5a).
Cites C-0dda429c60, C-303a605026, C-7f2ea3298c, C-b508b5b110, C-f3daa0fd5a
Pathway: standard
A decommissioning plan prepared by a registered professional is submitted to OPSB under Ohio law, with a bond and routine five-year updating (C-b6d40fe4d7, C-0dda429c60). The salvage question is an open item, not a documented dispute with the authority (C-7f2ea3298c). Timing details beyond the quoted text are not relied on.
Cites C-b6d40fe4d7, C-0dda429c60, C-7f2ea3298c
Impact likely: yes
A performance bond must be posted before construction and lease security is required, tying up capital or credit; the plan commits the project to funded removal to 36 inches and restoration (C-0dda429c60, C-00d4067593, C-f3daa0fd5a).
Cites C-0dda429c60, C-00d4067593, C-f3daa0fd5a
Supporting statements (11)
Each claim the row cites: the statement in the assessor's words, then the quote the engine found on the page.
C-00d4067593
Lease requires lessee to remove facilities to 36 inches depth and restore soil within 12 months after lease end, with security posted.
Quoted from page 1
Lessee removes all facilities to a depth of 36 inches and restores the soil within 12 months after
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · Page 1 · 2023-05-30
Source developer_document · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-0dda429c60
A performance bond with the Board as obligee, equal to the estimate, must be posted before construction, updated every five years and never reduced.
Quoted from page 1
Before construction it must post a
 performance bond, with the Board as obligee, equal to the estimate; the bond is updated every five years and is
 never reduced.
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 1 · 2023-03-20
Source developer_document · Claim type regulatory · Polarity presence · Confidence medium · Quote check exact, 100 of 100
C-303a605026
Decommissioning estimate in 2023 dollars is $11.6 million gross, $5.9 million salvage, $5.7 million net.
Quoted from page 2
Total                                            $11.6 million          $5.9 million             $5.7 million
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 2 · 2023-03-20
Source developer_document · Claim type cost · Polarity neutral · Confidence high · Quote check exact, 100 of 100
C-4e2febbe42
The easement ends two years after the project permanently stops operating; grantee must remove above-ground equipment and remove or leave buried cables at grantor's election.
Quoted from page 1
ends two (2) years after it permanently stops operating
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · Page 1 · 2022-11-03
Source public_record · Claim type constraint · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Filed under PE-05, PE-06
C-640e804855
Plan for battery removal and recycling at end of life in the decommissioning plan.
Quoted from page 2
Plan for battery removal and recycling at end of life in the decommissioning plan.
Battery Energy Storage System Fire Safety Narrative - Tamsin Ridge · DR-0014 · Page 2 · 2023-06-28
Source consultant_memo · Claim type recommendation · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Filed under EG-04, PE-06
C-7818388af6
Decommissioning plan and performance bond requirements of ORC 4906.21 to 4906.222 apply.
Quoted from page 1
decommissioning plan and performance bond requirements of ORC 4906.21 to 4906.222 apply.
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · Page 1 · 2023-03-28
Source agency_determination · Claim type regulatory · Polarity presence · Confidence high · Quote check exact, 100 of 100
C-7f2ea3298c
Whether OPSB accepts the estimate net of salvage ($5.7 million) or requires gross ($11.6 million) has not been settled.
Quoted from page 2
whether OPSB will accept the estimate net of salvage ($5.7 million) or
 require the gross figure ($11.6 million) has not been settled.
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 2 · 2023-03-20
Source developer_document · Claim type data_gap · Polarity neutral · Confidence high · Quote check exact, 100 of 100
Filed under PE-02, PE-06
C-b508b5b110
Salvage values rely on volatile scrap prices and could fall well short of the estimate.
Quoted from page 2
Scrap prices are volatile, and salvage could fall well short of these figures.
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 2 · 2023-03-20
Source developer_document · Claim type data_gap · Polarity neutral · Confidence high · Quote check exact, 100 of 100
C-b6d40fe4d7
Ohio law requires an engineer-prepared decommissioning plan submitted to the OPSB at least 60 days before construction, with removal ending within 12 months of cessation.
Quoted from page 1
the applicant must submit a comprehensive decommissioning plan prepared by a registered professional
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 1 · 2023-03-20
Source developer_document · Claim type regulatory · Polarity presence · Confidence medium · Quote check exact, 100 of 100
Filed under PE-02, PE-06
C-e278af1a95
The leases require removal and restoration within 12 months after they end.
Quoted from page 1
The leases also require removal and restoration within 12 months after they end.
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 1 · 2023-03-20
Source developer_document · Claim type constraint · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under PE-05, PE-06
C-f3daa0fd5a
The leases require separate security for each landowner, which the bond is intended to satisfy.
Quoted from page 2
The leases require separate security for each landowner, which the bond is intended to satisfy.
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · Page 2 · 2023-03-20
Source developer_document · Claim type constraint · Polarity presence · Confidence high · Quote check exact, 100 of 100
Filed under PE-05, PE-06
3 Permits and requirements
The requirements tied to the rows of this report, by level. Each quote from dated law is shown with its source, the version in force on the cut-off and the basis for it.
No requirement is tied to the rows of this report.
4 What is missing
The information requests the run raised for the rows of this report, by priority: what is missing, what follows from it, and whether it holds up the decision.
High priority (2)
IR-0a712115cd · High priority
Provide the financial assurance instrument or terms (bond, letter of credit, escrow, parent guarantee) for the project area, or confirm none exists.
	Missing evidence
	Financial assurance instrument or terms (bond, letter of credit, escrow, parent guarantee)

	Consequence
	Decommissioning and Financial Assurance is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


IR-9c85d7f357 · High priority
Provide the state or local decommissioning rule or permit condition for the project area, or confirm none exists.
	Missing evidence
	State or local decommissioning rule or permit condition

	Consequence
	Decommissioning and Financial Assurance is rated on partial evidence without it.

	Blocks the decision
	No

	Raised by
	completeness


5 Next steps and agencies
Next steps
Confirm with OPSB whether the bond may be net of salvage.
Align lease security with the OPSB bond and confirm bond form with the surety or lender.
Include battery removal and recycling in the decommissioning plan and estimate.
Agencies
OPSB
6 Basis and limits
This report is a desk review of the documents quoted above, as the engine read them for an information cut-off of 2023-08-01.
It is not a field survey and not a modelled study: this review made no site visit and ran no acoustic, hydraulic or other model. Where the record is silent, the report says what is missing; it does not fill the gap.
Every statement, figure and quote is the engine's record as written. The headings and connecting words are fixed text of this room, the same in every report.
Documents quoted (5)
Option and Lease Summary - Tamsin Ridge Solar and Storage Project · DR-0004 · 2023-05-30 · page 1
Preliminary Decommissioning Plan and Cost Estimate - Tamsin Ridge Solar and Storage Project · DR-0024 · 2023-03-20 · pages 1, 2
Underground Collection Line Easement Agreement - Parcel 7 · DR-0003 · 2022-11-03 · page 1
Battery Energy Storage System Fire Safety Narrative - Tamsin Ridge · DR-0014 · 2023-06-28 · page 2
OPSB Pre-Application Conference Summary - Tamsin Ridge Solar and Storage Project · DR-0026 · 2023-03-28 · page 1
Versions and data hashes
As the engine and the exporter recorded them. Hashes are SHA-256.
	Information cut-off
	2023-08-01

	Engine version
	2.11.0

	Prompt version
	2026-11-08.1

	Rows pack
	rows.json sha256 a018ecd7e4703bc1

	Federal pack
	federal.json sha256 8841c555ff35d20b

	State pack
	oh.json sha256 d4780705e1f18d09

	Local pack
	oh_carroll_county.json sha256 905cd3308848e7e8

	Data room manifest
	0c7e80d0ad17d1e3ed4060b9702e5b1905060ae2896e9aad796a57b590005832

	Audit chain
	valid (19 events)

	QA status
	PASS_WITH_WARNINGS

	Rendered at
	2026-11-10T15:42:40+00:00

	Run record (annex)
	66fca2c4c0bfa90df1e8efb79c0d2f426536b41f50a6a9b6869dd85e4554fd50

	Exporter
	Prism/room/exporter 1.4.0


Prism desk report · engine 2.11.0 · prompts 2026-11-08.1 · information cut-off 2023-08-01
	Prism desk report · engine 2.11.0 · prompts 2026-11-08.1 · information cut-off 2023-08-01
	Page 1 of 1



	Prism desk report · engine 2.11.0 · prompts 2026-11-08.1 · information cut-off 2023-08-01
	Page 1 of 1



